## DCO Implementation Plan
Task | Activities | Status
General Outreach and Education | Develop the Weekly Dose, a focused e-bulletin as method to share reliable information, spread evidence-based resources, spotlight effective interventions and announce educational events and clinical office hours | First issue sent on January 14, weekly thereafter Ongoing - every Thursday
| Establish a panel of subject matter experts to lead and contribute to weekly educational events and clinical office hours | Subject matter experts established and includes Infection Preventionist, Gerontological Nurse Practitioner, Pharmacist, Nursing Home Administrator and Licensed Nurses with nursing home experience Completed
| Hosting a weekly 45-minute virtual session, the first part of the session is an interactive educational event and the second part focus on clinical updates or guidance with the opportunity for participations to ask questions and share experiences. | First event held on January 19, weekly thereafter Ongoing weekly - every Wednesday The Vaccine QII nursing homes will be targeted for the weekly 45-minute virtual sessions. In addition, the sessions will be open to nursing homes in the service area as means of providing support during this critical time of the public health emergency. The second event held on January 26 was open to the service area nursing homes, weekly thereafter
| Develop a 12 - week curriculum framework | Developed curriculum through May 4, 2022
| HQI will utilize feedback from the virtual sessions and technical assistance to help develop future sessions. | Utilizing polling, Q&A and chat functions Ongoing
| Utilize technical assistance feedback, NHSN and self-reported resident booster data to identify possible cohorts for smaller learning groups | Not started, in process of collecting data
| Develop monthly vaccine office hours - Simple Strategies Standup | June 14, 2022 start - In progress
| Develop Infection Preventionist affinity group - Infection Program - Prepare, Prevent, Protect | June 21, 2022 start - In progress
Technical Assistance - 20 Encounters Per Week | For resident booster referrals that are also resident/staff vaccination referral, assign existing Quality Improvement Advisor to support nursing home | Completed
| For resident booster referrals that are also existing TR-QII IP referrals, assign existing Quality Improvement Advisor to support nursing home | Completed
| As new TR-QII IP referrals are received assign any outstanding resident booster referral to designated Quality Improvement Advisor | Completed
| Identify and establish human capital to provide additional TR-QII support | Subcontractor quotes obtained January 25, in process of awarding contact (1) Subcontractor hired, added additional contractor 2/23/22 Recruitment and interviewing activities are in progress (1) Team member hired, recruiting additional staff
Data Collection and Monitoring | Establish a data collection process for capturing and monitoring nursing home self-reported resident booster data | Established a process for nursing homes to self-report resident booster data. The data is then analyzed and posted to a dashboard where HQI can monitor data submission and trends.
| Request and remind nursing homes to submit resident booster data at least monthly during technical assistance and via routine messaging. | Data submission reminder incorporated into Weekly Dose, first issue January 14. Automated monthly reminder in development. Completed
| Establish dashboard to monitor and trend resident and staff vaccination data, including booster data, via NHSN and CMS Care Compare | Completed
| Developed nursing home data reports demonstrating resident and staff primary series and booster vaccination performance. | Completed
Vaccine/Booster Clinics | Conduct environmental scan to identify existing activities or programs to support vaccinations in nursing homes i.e., health departments, trade associations, Medical Reserve Corp, school of pharmacy, pharmacy vendors, etc. | In progress Ongoing, NH being used to determine needs for clinics In progress of developing a NH needs assessment
| Identify nursing homes need during technical assistant by utilizing the Qualtrics questionnaire to identify access and supply issues. | Ongoing

## RIR
QIN/QIO Name: Health Quality Innovators (HQI)
Region: KS, MO, SC, VA
Percentage of Current Residents with a Completed Vaccination who Received a COVID-19 Vaccine Booster at Any Time (Vaccine QII Booster Referrals)
RIRs Since Start of DCO (1/16/22)

## January 2022
QIN/QIO Name:
Region:
Assigned COR:
Date:
Topic Area |  | Questions to Drive Success | Week 1 | Week 2 (1/12 - 1/18) *First week of DCO | Week 3 (1/19 - 1/25) | Week 4 (1/26 - 2/1) | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? |  | Environment Scan & NH Technical Assistance (TA) | Ongoing | Ongoing | Identified that each State's Health Department and Schools of Pharmacy or Pharmacy Trade Associations are continuing to provide onsite vaccine clinic assistance. |  |  |  | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? |  | 0 | 0 | 0 |  |  |  |  | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? |  | 0 | 0 | 0 |  |  |  |  | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? |  | 1) Develop the Weekly Dose, a focused e-bulletin as method to share reliable information, spread evidence-based resources, spotlight effective interventions and announce educational events and clinical office hours 2) Established a panel of SMEs to lead and contribute to weekly education events and clinical office hours 3) Began developing a 12 - week curriculum framework | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events, shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events, shares updated guidance and resources | First Weekly Dose issue sent on January 14, weekly thereafter Curriculum in process |  |  |  | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement |  |  | 7 (webinar) | 35 (webinar) |  |  |  |  | Qualtrics - General Outreach - column EF
| 2c. | What is the duration of events and what relevant topics have been shared? |  |  | .75 minutes - First education/clinical office hours: "What You need to Know About Vaccines Today" 1) Vaccine tracking 2) Demo HQIN Vaccine tracking sheet for residents & staff including primary & booster vaccines. 3) CMS guidance re: staff vaccine mandates 4) CDC update re: interval for receiving Pfizer or Moderna vaccine | 1 hour - Education/clinical office hours - "Turnkey Solutions for Vaccinations" 1) HQIN Vaccine Administration Process Guide 2) Clinic Case Study 3) Practices for month vaccine administration/clinic 4) Sharing tips that work 5) CMS COVID-19 Vaccination Requirements for Health Care Providers and Suppliers 6) V-Safe |  |  |  |  | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? |  | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Ongoing | Ongoing |  |  |  |  | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | [8 empty] | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? |  | Provided TA, education, clinical office hours and resources related to CDC and CMS guidance | Provided TA, education, clinical office hours and resources related to CDC and CMS guidance | Provided TA, education, clinical office hours and resources related to CDC and CMS guidance |  |  |  |  | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? |  | 1) Establishing a data collection process for capturing and monitoring nursing home self-reported resident booster data 2) Establishing a dashboard to monitor and trend resident and staff vaccination data, including booster data, via NHSN and CMS Care Compare 3) Establishing process to collect monthly resident booster data from nursing homes | 1) Establishing a data collection process for capturing and monitoring nursing home self-reported resident booster data 2) Establishing a dashboard to monitor and trend resident and staff vaccination data, including booster data, via NHSN and CMS Care Compare 3) Establishing process to collect monthly resident booster data from nursing homes | Utilization of HQI dashboard to monitor and trend booster rates utilizing NHSN and facility reported data | Completed setup of data systems/dashboards |  |  |  | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | [8 empty] | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09
|  | Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time | 30080 | 30310 | 30383 | 30213
|  | Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time | 8343 | 8821 | 10309 | 11339
|  | Residents COVID-19 Vaccine Booster Rate: | 27.74% | 29.1% | 33.93% | 37.53%

## February 2022
QIN/QIO Name: Health Quality Innovators (HQI)
Region: KS, MO, SC, VA
Assigned COR: P. Nicole Crenshaw
Topic Area |  | Questions to Drive Success | Week 1 (2/2-2/8) | Week 2 (2/9-2/15) | Week 3 (2/16-2/22) *Started utilizing this DCO reporting format | Week 4 (2/23 - 3/1) | Week 5 | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | Environment Scan & NH Technical Assistance (TA) | Ongoing | Ongoing | Ongoing assessment of needs via direct nursing home outreach. Scheduled a 2nd vaccine clinic for nursing home on 3/17/22; first clinic held 2/17/22. |  | Partnered with Virginia Department of Health and Virginia Pharmacy Association to conduct vaccine clinics for 2 NHs |  |  |  | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 0 | 0 | 2 | 0 | [5 empty] | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | N/A | N/A | Staff = 5 Residents = 95 | N/A | [5 empty] | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events, shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events, shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events, shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events, shares updated guidance and resources | [5 empty] | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | 8 (webinar) | 9 (webinar) | 19 (webinar) | 47 (webinar) | [5 empty] | HQI internal report
| 2c. | What is the duration of events and what relevant topics have been shared? | .75 Education/clinical office hours - "Booster Myths: Science vs. Sorcery" 1) Reviewed common myths and fears 2) Vaccine facts to share with empathy 3) COVID-19 Vaccine Educational Resources for LTCFs including CDC and CMS resources | 50 mins Education/clinical office hours - "Boosting Confidence" 1) CDC Video - Booster Shots Needed Against Omicron 2) Evidence/data review 3) Why boosters are critical for residents | .5 - "Hit the Easy Button: Coordinating Vaccine Co-administration is Good" 1) CDC Guidance on Co-administration of vaccines i.e. flu, pneumonia, shingles, etc. 2) Vaccines reduce illness and readmissions 3) New guidance for pneumococcal vaccination | 0.5 - "Hitting the Mark: Correct I.M. Administration" 1) Resident education about the booster vaccine and process 2) Understanding the appropriate landmarks for I.M. injection 3) Appropriate techniques for I.M. injections 4) Potential complications 5)How to provide emotional support to residents. | [5 empty] | Qualtrics - General Outreach - column EE & HQI internal tracking
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | [5 empty] | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? |  |  | Direct TA with 31 leaders | Direct consultation with 22 leaders to assess vaccination program and conduct root cause analysis for any identified gaps. Including: 1) Coaching on motivational interviewing techniques 2) Help to develop vaccine champions 3) How to use vaccine data 4) Dispel misconceptions and misinformation 5) CDC NHSN data reporting 6) Provided vaccine safety and efficacy information | [5 empty] | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | Provided guidance during 1:1 consultation Utilized CDC Resources for Education Adult Patients about Vaccines during the weekly education/office hours event. | Provided guidance during 1:1 consultation Utilized CDC Resources for Education Adult Patients about Vaccines during the weekly education/office hours event. | Provided guidance during 1:1 consultation Utilized CDC Resources for Education Adult Patients about Vaccines during the weekly education/office hours event. | Provided guidance during 1:1 consultation Utilized CDC Resources for Education Adult Patients about Vaccines during the weekly education/office hours event. |  |  | COVID-19 outbreaks and administration of therapeutics impacts the eligibility/timing of vaccination Nursing homes that have a high volume of short stay residents have shortened window of opportunity to administer the vaccine | Support nursing homes in accurate tracking of vaccination administrator and status to include at time of admission and discharge | A nursing home DON has setup a process to schedule any discharged residents needing a vaccine for the next vaccine clinic hosted at the facility. | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | Utilization of HQI dashboard to monitor and trend booster rates utilizing NHSN and facility reported data | Utilization of HQI dashboard to monitor and trend booster rates utilizing NHSN and facility reported data | Utilization of HQI dashboard to monitor and trend booster rates utilizing NHSN and facility reported data | Utilization of HQI dashboard to monitor and trend booster rates utilizing NHSN and facility reported data | [5 empty] | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? |  |  | 14 | 26 | [5 empty] | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Resident Booster Vaccine QIIs Rate Tracking | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06
|  | Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time | 30575 | 30379 | 30261 | 30139
|  | Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time | 12415 | 13034 | 13657 | 14531
|  | Residents COVID-19 Vaccine Booster Rate: | 40.61% | 42.9% | 45.13% | 48.21%
|  | % RIR since DCO Start: | 0% | 5.663% | 11.15% | 18.74%

## March 2022
QIN/QIO Name:
Region:
Assigned COR:
Date:
Topic Area |  | Questions to Drive Success | Week 1 (3/2-3/8) | Week 2 (3/9-3/15) | Week 3 (3/16-3/22) | Week 4 (3/23 -3/29) | Week 5 3/30 -4/5) | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | Ongoing assessment of needs via direct nursing home outreach. | Ongoing assessment of needs via direct nursing home outreach. | Ongoing assessment of needs via direct nursing home outreach. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Needs assessment was distributed 3/24 as scheduled. Next step will be to analyze responses. Received seven response to the needs assessment as of 4/5/22. Based upon these responses, and 1:1 consultation reports, vaccine clinics are not a challenge for the majority of nursing homes in our service area. The challenges are related to residents/families refusing the vaccine due to low vaccine confidence and hesitancy and understanding of why a booster vaccine is needed if one has already had COVID-19 or will get COVID-19 anyway. In order to have a clinic, consent much be obtained first because a clinic cannot be scheduled until one knows the supply of vaccine needed due the shelf life of the vaccine. | COVID-19 outbreaks and administration of therapeutics impacts the eligibility/timing of vaccination Nursing homes that have a high volume of short stay residents have shortened window of opportunity to administer the vaccine Due to HQI's human capital capacity issues, we have not yet connected with all referred nursing homes. This limits our ability to fully assess vaccine access or clinic needs. One home has implemented a policy that they will not be offering the vaccine because they serve a short stay population with an average length of stay of 2 weeks. This is a small, rural long term care unit (LTCU) within a hospital. When we attempted to discuss options, the director noted it was a hospital executive decision. | Support nursing homes in accurate tracking of vaccination administrator and status to include at time of admission and discharge Distributing a needs assessment 3/24/22 to referred nursing homes as a method for identifying where nursing homes need assistance. The assessment includes vaccine access, clinic, education and resource needs. In process of training Quality Improvement Advisors (QIAs) how to conduct and capture technical assistance related to identifying and assisting with vaccine clinic needs. | 3/2: A facility is assisting residents who are being discharged home before receiving their next scheduled vaccine to setup appointments with the local health department. 3/2: A facility is providing residents who are discharged from the facility before being eligible for their booster vaccine with their vaccine card and assisting the resident with providing vaccine status to their community pharmacy and the due date of next vaccine. 3/9: A rural KS nursing home shared that if a responsible party did not consent they received a personal phone call and the facility provided re-education. This facility found that most of the time a education went a long way. 3/22: A facility works with affiliated sister facility to share vaccines to ensure no vaccine is wasted. 3/22: Identified facilities that have established bi-weekly vaccine clinics with their pharmacy vendor. | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 0 | 0 | 0 | 2 (second HQI clinic for these NHs) | 0 |  |  |  |  | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | N/A | N/A | N/A | 12 for one NH, pending results from second NH | N/A |  |  |  | At the start of the vaccine booster referral for the facility noted here hosting the clinic, had 12% of their residents boosted. Their rate as of 3/24 is 98.48% (65 of 66 eligible residents are now boosted). HQI assistance in organizing the onsite clinic has not only greatly improved their booster rates, but it has allowed the facility time to focus on hiring to address staffing challenges. | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Launched "What Works: Best Practices & Innovative Ideas" (HQIN.org - COVID-19) | It is challenging for nursing homes to attend weekly webinars. On average, 24 nursing homes have attend the last seven weeks' webinars. Reaching residents and families directly is challenging. Existing resources from various agencies to build educational content is geared toward staff or general public. It is not specific to the resident and family audience. During consultation calls, office hours and needs assessment feedback we identified the following: 1) Feedback that residents and families are becoming angry when facility staff continue to ask for vaccination consent. So, facility staff stop offering the vaccine. 2) Feedback that residents and families have low vaccine confidence and are vaccine hesitant. 3) When asked how facilities publicly promote the COVID-19 vaccine, some have responded that they don't promote it publicly. They don't use bulletin boards or post information in high traffic areas. 4) We've had Infection Preventionist ask if we have a forum where they can connect with their peers to develop or improve their knowledge. Often times individuals are promoted into the role of Infection Preventionists with minimal to no experience. The CDC or other trainings are provided, but individuals are seeking the opportunity to connect with peers and learn. Creating turnkey educational resources for the resident/family audience to reduce the burden on the nursing homes in promoting the COVID-19 vaccine. | 3/30/22: The weekly webinar will introduce evidence based patient and family centered care decision framework. Two Administrators will share their experience building trust with residents and families. One will share how the facility team engaged residents, families and community members to achieve a 100% resident primary and booster vaccine rate and staff rate of >90%. 4/13/22: HQI is hosting a webinar teaching nursing home leaders to facilitate conversations with residents and families about immunization. A slide deck that facilities can use to host resident council, family council or town hall meetings will be provided as a companion resource. Launching "What Works: Best Practices & Innovative Idea Sharing" webpage in April. This webpage will be used to share best practices that we've collected from nursing homes across our region. In development: An educational video targeted at the resident and family audience for use by nursing homes. Nursing homes will be able to distribute the video to residents and families via email or text messages and played over closed circuit TV where available. Will utilize needs assessment findings to help develop future educational topics. Will continue weekly webinars through April. Developing plan to move from weekly webinars to monthly or affinity groups in May in an effort to focus more on identified needs and data. Developing a resident/family resource that can be "leave behind" if an individual declines to vaccine with information as to who to contact if they later have questions or reconsider vaccination. Developing resources that target the vaccine confidence and hesitancy for residents and families including one page information sheets and resident/family council vaccine education PowerPoint template that facilities can individualize to reflect their vaccine program. Developing a "Bulletin Board Package" that will contain ready to post resources that can be publicly displayed to inform staff, residents, families and visitors. In May, we will begin monthly vaccine office hours in order to be able to keep nursing homes informed of new guidance, spread best practices and answer questions. Will launch a Infection Preventionist affinity group May/June timeframe. The goal will be to provide Infection Preventionist with the knowledge and skills to effectively led infection prevention and control programs, including vaccine programs. |  | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | 47 (webinar) | 13 (webinar) | 28 (webinar) | 45 registered and 8 attended (webinar) | 58 registered and 19 attended (webinar) | Stakeholders began to promote the April vaccine webinar series in their newsletters/listserv as of 3/24 and going forward. Will monitor registration and attendance to see if stakeholder promotion results in higher participation. | It is challenging for nursing homes to attend weekly webinars. | To promote the live events and access to slides and recordings, HQI is launching a brief recorded promo message that will be included in the Weekly Dose. The promo message explains the purpose of the weekly ed/clinical sessions and how to access slides and resources if one can't attend the live event. We are also monitoring the number of people that are accessing slides: 3/2 event - 38 people viewed the slides, 3/9 event - 12 people viewed the slides. Providing nursing homes with a weekly vaccine series through April 27, 2022 and the ability to register for all events at once, in advance. The goal is promote topics of interest/need and allow for advance scheduling. The week of March 21, HQI requested trade associations and other partners i.e. health departments, other consultant organizations, etc. to promote the vaccine series via their newsletters and listserv. |  | Qualtrics - General Outreach - columns AJ,AK, AL
| 2c. | What is the duration of events and what relevant topics have been shared? | 0.5 - "Frontline Staff: Supporting Vital Caregivers" 1) Application of updated knowledge to identify the evolving role of frontline staff 2) Discussed how to empower staff and provided resources for well-being and vaccine promotion 3) Discussed benefits of COVID-19 booster vaccination for frontline staff and 4) Discussed how to address visitor, residents and staff confusion regarding community transmission rates | 50 mins. - "COVID-19 Vaccination Clinic Best Practices Strategizing for Success: Lessons Learned from the Frontline" - Guest speaker Johnson County Health Department, Kansas 1) Reviewed vaccine clinic process (pre clinic, clinic, post clinic) 2) Reviewed internal tracking tool 3) Marking the clinic 4) Overcoming vaccine access challenges | 50 mins - "Aligning Resident COVID-19 Vaccine and Boosters with QAPI" 1) Utilizing data to monitor weekly/monthly improvement 2) How to implement systems to support the immunization program 3) Identifying root cause for residents, or families, declining the booster vaccine 4) Weekly communication: "Believing myths about COVID-19 vaccines is not the same as getting the facts" | 30 mins - "We Can Boost the Boosters: What You Need to Know About COVID-19 Vaccines and Boosters" 1) Review of publicly available data on Care Compare 2) Review of "what is COVID-19" 3) Addressing the question "I'm vaccinated why do I need a booster" 4) CDC Interim IPC recommendations to prevent COVID-19 spread in nursing homes 5) Additional dose recommendations 6) How to apply QAPI to the vaccination program | 75 minutes - "Rebuilding Trust: Partnering for Improved Outcomes" 1) Guest speakers: Executive Director, KS Advocates for Better Care and Administrator, Mount St. Mary 2) Impact of COVID-19 on residents and families 3) How to move forward with resident and family engagement 4)Decision making process withing a Patient and Family Centered Care (PFCC) framework 5) Nursing home best practices for resident and staff vaccination rates |  |  |  | 3/2: Providing written message during the weekly education/office hours session that nursing homes can send via text or emails to residents and/or staff promoting vaccination. 2/23 session message: "You save lives with every vaccination. In one year, the COVID-19 vaccines saved 1.1 million lives" (www.advisory.com) 3/2 session message: "Although the booster wanes over time, it still provides sturdy protection against landing in the hospital". | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse |  |  |  |  | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | Direct consultation with 33 leaders to assess vaccination program and conduct root cause analysis(RCA) for identified gaps. Including: 1) CDC NHSN data reporting 2) Tracking and interpreting data 3) Help to develop vaccine champions 4) Coaching on motivational interviewing techniques 5) Provide resources from trusted organizations/sites | Direct consultation with 47 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Public display & recognition staff/resident vaccine data 2) Coaching on motivational interviewing 3) Help develop vaccine champions 4) Provide vaccine safety/efficacy information 5) CDC NHSN data reporting | Direct consultation with 34 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Help to develop vaccine champions 2) Public display & recognition staff/resident vaccine data 3) AHA COVID-19 Vaccine Communications Toolkit | Direct consultation with 27 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Help to develop vaccine champions 2) Public display & recognition staff/resident vaccine data 3) CDC COVID-19 Booster Shots | Direct consultation with 45 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) NHSN reporting education/support 3) Coaching on motivational interviewing techniques 4) Help developing vaccine champions 5) Public display of NH vaccination rates over time | As of 3/24, (24) nursing homes have "no contact attempted" and (14) nursing homes have been unresponsive to five attempts to contact. This does not mean the remaining nursing homes have responded to outreach. We will continue to contact the facilities and note status when we reach 5 contact attempts. As of 4/5, we have attempted to contact all referred nursing homes and (14) nursing homes have been unresponsive to five attempts to contact. | 3/8: Receiving feedback that residents/families are refusing booster since they, or their loved one, is fully vaccinated and don't understand why they have to receive another injection. Inability to ramp up staffing to meet referral demands. | 3/8: In response HQI is providing nursing homes with strategies and talking points, including myths and facts. We also are providing data that shows the efficacy of vaccines in nursing homes. HQI is also developing a vaccination/booster educational PowerPoint presentation that nursing homes can use during resident and family council meetings. The presentation will include scripted talking points for ease of implementation. HQI has secured two subcontractors to assist with TR-QII referrals. And we continue to hire staff as current resources continue to be at max capacity. As of 3/16/22, all Vaccine QIIs have been assigned to QIAs. The QIAs have begun outreach to their assigned facilities. Assessing the number of nursing homes not yet contacted and the number of nursing homes unresponsive to outreach. As of 3/28 one new HQI team member started and another is pending a start date of 4/1. For a total of (2) new hires. New hire started April 1. Pending an additional new hire April 11. | 3/8: A Director of Nursing (DON) is personally calling each family to relate her own personal story of recently working in acute care explaining that in her experience, vaccinated & boosted patients had far better outcomes than unvaccinated. This personal touch has been well-received in a community with very low vaccination rates. The nursing home now has a 89% booster vaccination rate. | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine Booster resources. Utilization of CDC resources for severe respiratory issues related to COVID-19 and CDC COVID-19 data during the week education/office hours event. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. Utilization of CDC COVID-19 booster shots and Public Health Communications Collaborative resources. Collaboration with a local department of health in KS during the weekly education/clinical office hours session. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. Utilization of CDC COVID-19 booster shots and Public Health Communications resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. Utilization of CDC COVID-19 booster shots and Public Health Communications resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. Utilization of CDC COVID-19 booster shots and Public Health Communications resources. |  |  |  |  | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | Utilization of HQI dashboard to monitor and trend booster rates utilizing NHSN and facility reported data | Utilization of HQI dashboard and NHSN data continues | Utilization of HQI dashboard and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Based on the Quartics/CMS reporting criteria (70) out of (251) nursing homes are reporting >= 90% booster rates. This is an improvement of (22) nursing homes from previous month. Based on the Quartics/CMS reporting criteria (90) out of (309) nursing homes are reporting >= 90% booster rates. This is an improvement of (10) nursing homes from previous report. | 1) The resident booster rates are in flux based on residents testing positive for COVID-19, antibody treatment and admissions/discharges. 2) The difference between the CDC NHSN booster eligibility data and CMS eligibility data continues to propose challenges. Nursing homes are pushing back in having to report data different ways to different federal agencies. Often times the data based on the CMS definition is higher than current referral threshold and some facilities have achieved the 90% goal. 3) This is also challenging for QIN-QIOs to monitor. The Vaccine QII referrals are based on the NHSN data but then QIN-QIOs collect/monitor according the CMS definition; which doesn't follow quality improvement principles for analyzing data. 4) The public CDC NHSN data and the CMS Compare Care data are pulled from NHSN. 5)The NHSN data has an approximately 11-day lag period: for example, on Thursday, March 17th, data through reporting week ending Sunday March 6th was made available. 6) The CDC’s resident COVID-19 vaccine booster rate is defined as the percentage of residents in nursing homes with complete COVID-19 vaccination receiving an additional primary or booster dose. Numerator/denominator definitions: • Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 vaccination at Any Time • Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time 7) The self-report booster rates via Qualtrics uses the CMS definition. The primary difference between CMS’s definition and CDC’s definition is in the denominator: CMS asks that the denominator includes only the following: • Denominator: Number of residents who are eligible to receive the COVID booster (including all NH residents who are eligible MINUS any medical or religious exemptions AND temporary deferrals due to illness or receipt of monoclonal antibody treatment) 8) To summarize, the CDC’s denominator broadly looks at all residents with a completed COVID-19 vaccination (regardless of whether they are eligible for the booster or not), whereas CMS’s definition takes into account timing of the completed primary series and any exemptions or deferrals | 1) HQI is collecting and tracking both NHSN and self-reported (CMS data) 2) We contact nursing homes both via email and phone calls to encourage/collect the self-reported data 3) We integrate data into the weekly education and clinical office hours sessions 4) It would be helpful to nursing homes if the CDC and CMS could align definitions as this would ease reporting burden and reflect consistent data for public reference and quality improvement. During technical assistance calls HQI identified some nursing homes were reporting (0) boosters, which was an error in reporting. Based on this information, we analyzed the NHSN data to stratify nursing home reporting rates. Using this data we are adjusting our technical assistance approach. Rather than simply working through assigned nursing homes, QIAs will prioritize the nursing homes reporting (0) boosters in NHSN for technical assistance. | HQI is utilizing individual facility Vaccine QII reports to engage nursing homes in using data to drive improvement. The Vaccine QII report is based on NHSN and Care Compare vaccine data (see 3/23/22 email attachment for sample report). | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | 58 | 60 | 62 | 35 | 64 |  |  |  |  | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13
|  | Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time | 30004 | 30137 | 30186 | 30216 | 30076
|  | Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time | 14668 | 16499 | 16567 | 17520 | 17744
|  | Residents COVID-19 Vaccine Booster Rate: | 48.89% | 54.75% | 54.88% | 57.98% | 59%
|  | % RIR since DCO Start (1/16/22): | 20.4% | 34.83% | 35.16% | 42.8% | 45.3%

## April 2022
QIN/QIO Name: Health Quality Innovators (HQI)
Region: KS, MO, SC, VA
Assigned COR: P. Nicole Crenshaw
Topic Area |  | Questions to Drive Success | Week 1 (April 6 - April 12) | Week 2 (April 13 - April 19) | Week 3 (April 20 - April 26) | Week 4 (April 27 - May 3) | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Quality Improvement Advisors (QIAs) are sending the needs assessment to the nursing homes that have not responded to outreach efforts in attempt to assess current vaccine status and needs. |  |  |  | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 1 | 1 (pending Qualtrics entry) | 0 | 0 |  |  |  |  | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | 24 | 11 | 0 | 0 |  |  |  |  | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Beginning in May, we will transition to monthly "office hour calls" focused on addressing current updates and providing SMEs for Q&As Beginning in June, we will transition to monthly educational events targeted to Infection Preventionist Developing resources targeted at resident/family education to include "Why Do We Need a COVID-19 Booster" 1 page factsheets; Resident/Family Council educational materials; Bulletin Board Bundle and "leave behind" material for those residents/families that refuse the vaccine which provides contact information if they have further questions or change their decision. Last weekly education and office hours event will occur May 4, 2022. Beginning in June we will host a monthly "Simple Strategies Stand-up". This will be our office hours and is structured to give nursing homes updates, guidance and opportunity to ask SMEs questions. We will also kick off our Infection Program: Prepare, Prevent, Protect educational and networking monthly event in June. The target audience will be infection preventionists with the goal to increase their skills and knowledge so they are seen as the SME in their respective facility. |  |  |  | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | 60 registered and 11 attended (webinar) | 80 registered and 24 attended (webinar) | 83 registered and 36 attended (webinar) | 78 registered and 26 attended (webinar) |  |  |  |  | Qualtrics - General Outreach - column EF
| 2c. | What is the duration of events and what relevant topics have been shared? | 1 hour - Highlighting Best Practices: The St. Louis Post Acute and Long-term Care Roundtable 1) A medical director served as guest speaker and shared how he helped to establish an acute care and post-acute care collaborative in the St. Louis, MO market. 2) Goal of the collaborative is to improve transitions of care 3) During the pandemic the collaborative pivoted to address care needs due to COVID-19 4) How to use champions across continuum of care | 1 hour - COVID-19 Booster Vaccines: Using Data and Science to Guide Messaging 1) Utilize infection preventionists (IPs) and other respected staff to promote vaccines 2) Obtain information about the historical impact of vaccines to foster awareness about vaccine safety 3) Gain knowledge about the safety and efficacy of COVID vaccine boosters 4) Presentation can be adapted for individual facility use during town hall meetings or family council meetings 5)Two Administrators and an Director of Nursing (DON) shared how they provided vaccine and booster education -family council conference calls (best results) -DON met 1:1 with family/caregivers -Resident admission screening - Medical director 1:1 with residents -written vaccine/booster action plans -letters, emails -social media -administrator phone calls and 1:1 with families/caregivers (best results) | 45 minutes - Including COVID-19 Vaccination Boosters in Your Discharge Planning Process 1) Discuss tools and plans that support needs for taking care of residents who will be discharged 2)Determine ways to facilitate getting vaccination information to the right people 3) Learn how readmissions are prevented when discharges are planned, safe and thorough 4) Helping residents get proof of vaccination 5) Managing next dose as part of vaccine clinic 5) Model a safe transition of care i.e. warm handoffs 6) Make vaccinations part of medication orders in the discharge plan | 47 minutes - Pandemic Prepared: Partnering with Pharmacists 1) Describe the factors that may contribute to polypharmacy 2)Identify at least 4 specific areas pharmacists can assist with medication and dosing 3) Explain why LTC pharmacists add value to the nursing home clinical and staff team 4) Discuss ways pharmacists can address COVID-19 hesitancy 5) Introduced new "COVID-19 Booster Shots" flyer that can be posted on facility bulletin board or used as handouts. Covers who should get the vaccine, safety of vaccine and why get the vaccine. Resource can be found at hqin.org/resource center | Evaluation comments: "Thank your so much, the sessions have helped us trouble shoot better ways to provide safe and effective discharges for our residents" "Thank you for your suggestions keeping documentation on unvaccinated and those with medical exemptions" |  |  |  | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse |  |  |  |  | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | Direct consultation with 24 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) NHSN reporting education/support 3) Coaching on motivational interviewing techniques 4) Help developing vaccine champions 5) Public display of NH vaccination rates over time | Direct consultation with 17 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) NHSN reporting education/support 3) Coaching on motivational interviewing techniques 4) Help developing vaccine champions 5) Public display of NH vaccination rates over time | Direct consultation with 56 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) NHSN reporting education/support 3) Coaching on motivational interviewing techniques 4) Public display of NH vaccination rates over time | Direct consultation with 17 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) NHSN reporting education/support 3) Coaching on motivational interviewing techniques 4) Public display of NH vaccination rates over time | As of 5/3, we have attempted to contact all referred nursing homes and (18) nursing homes have been unresponsive to five attempts to contact. |  |  |  | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. Utilization of CDC COVID-19 booster shots and Public Health Communications resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. Utilization of CDC COVID-19 booster shots and Public Health Communications resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. Utilization of CDC COVID-19 booster shots and Public Health Communications resources. CMS Calculator for Quarantine or Isolation | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. |  |  |  |  | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Based on the Quartics/CMS reporting criteria (122) out of (366) nursing homes are reporting >= 90% booster rates. This is an improvement of (5) nursing homes from previous report. |  |  |  | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | 35 | 41 | 92 | 43 |  |  |  |  | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10
|  | Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time | 30202 | 30037 | 30017 | 30075
|  | Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time | 18528 | 19330 | 20170 | 20301
|  | Residents COVID-19 Vaccine Booster Rate: | 61.35% | 64.35% | 67.2% | 67.5%
|  | % RIR since DCO Start: | 51.08% | 58.49% | 65.48% | 66.24%

## May 2022
QIN/QIO Name: Health Quality Innovators
Region: KS, MO, SC, VA
Assigned COR: Nicole Crenshaw
Topic Area |  | Questions to Drive Success | Week 1 05/4/22 - 05/10/22 | Week 2 05/11/22 - 05/17/2022 | Week 3 05/18/2022 - 05/24/2022 | Week 4 05/25/2022 - 05/31/2022 | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach. | Ongoing assessment of needs via direct nursing home outreach. |  |  |  |  | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 0 | 0 | 0 | 0 |  |  |  |  | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | 0 | 0 | 0 | 0 |  |  |  |  | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | Hosting a weekly virtual education and clinical combo event Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources |  |  |  |  | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | 32 registered and 16 attended (webinar) | Due to transitioning to monthly events, we are also now monitoring access to our online resources and recorded events. For May 1 - 17 the top accessed resources are: 1) COVID -19 Booster Shots Flyer - 43 unique views 2) Bulletin Board Bundles - 32 unique views 3) Booster Questions Poster & Handout - 29 unique views 4) COVID-19 Vaccination Booster Action Plan - 16 unique views | Due to transitioning to monthly events, we are also now monitoring access to our online resources and recorded events. For May 16 - 22, 2022 the top accessed resources are: 1) Bulletin board bundles - 20 unique views 2) Safe linen management action plan template - 18 unique views 3) How do we protect ourselves during a pandemic flyer - 18 unique views 4) Safe visitation in nursing homes - 14 unique views | Due to transitioning to monthly events, we are also now monitoring access to our online resources and recorded events. For May 23 - 29, 2022 the top accessed resources are: 1) Safe visitation in nursing homes - 28 unique views 2) Bulletin board bundles - 13 unique views 3) Booster questions handout/poster - 5 unique views | Transitioned to (2) monthly events. Simple Strategies Standup (office hours event) begins June 14 and Prepare, Prevent, Protect (educational event) begins June 22. |  |  |  | Qualtrics - General Outreach - column EF
| 2c. | What is the duration of events and what relevant topics have been shared? | 48 minutes - "Back to the Future: Living Safely in the Time of COVID-19 1) Discuss how lives have been saved by caring staff providing infection prevention, appropriate PPE, vaccination clinics and patient and family education 2)Review tools that can take us into the future prepared for this pandemic 3) Share resources that can help minimize infections and avoid serious illness 4) Review health equity data related to COVID-19 and vaccination | N/A | N/A | N/A |  |  |  | Shared during Weekly Dose Office Hours from an attendee: "At work, it's evident there is still a fear of needles. That is the only reaction at our vaccine clinics that I saw – someone getting faint, jittery right after.​ So we learned, don't let someone just get up and quickly walk away. Talk to them, delay them for a few seconds to make sure they are fine." HQI shared the AHRQ Intramuscular Injections - Best Practices for Safe Vaccine Administration in Nursing Homes (ahrq.gov) | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | Administrator, DON and Infection Prevention Nurse are included in the weekly virtual event invitation and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse |  |  |  |  | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | Direct consultation with 15 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) NHSN reporting education/support 3) Coaching on motivational interviewing techniques 4) Public display of NH vaccination rates over time | Direct consultation with 15 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) NHSN reporting education/support 3) Coaching on motivational interviewing techniques 4) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers | Direct consultation with 19 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) NHSN reporting education/support 3) Coaching on motivational interviewing techniques 4) Help develop vaccine champions as advocates and trusted messengers | Direct consultation with 25 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Public display of nursing home vaccination rate over time using data 3) Coaching on motivational interviewing techniques 4) Help develop vaccine champions as advocates and trusted messengers 5) Facilitate discussion to dispel misconceptions and misinformation | As of 5/31, we have attempted to contact all referred nursing homes and (17) nursing homes have been unresponsive to five attempts to contact. | Identified that some nursing homes are not posting COVID-19 vaccine information publicly for staff, resident, family or visitor reference. Facilities lack information that can be "left behind" for staff, resident or families/responsible parties that may refuse the COVID-19 vaccine. | HQI has launched a "Bulletin Board Bundle". We developed and released information that nursing homes can post throughout their facility as public education/messaging. Current bundle resources include: 1) COVID-19 Booster Vaccines: Using Data and Science To Guide Messaging 2) Discharge Compliance with Vaccinations: Vaccination Plans at Discharge for Staff and Residents 3) Supporting and Building Our Best Team 4) New resident/family resource - Why Do We Have Pandemics? This one page flyer explains what a pandemic is and key actions we can take during a pandemic to safely transition to the future. Resources can be found on the HQIN Resource Center www.hqin.org HQI developed and released a Booster Questions Poster and Handout resources. The poster can be posted throughout a facility and the handout is intended to be used as "leave behind". The nursing home is to personalize the poster and handout with the facility specific point of contact for questions related to the COVID-19 vaccine. The goal is to provide a point of contact for further questions and assistance should an individual change their decision and agree to the COVID-19 vaccine. Resources can be fond the HQIN Resource Center www.hqin.org |  | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. Also assisted with accurate NHSN reporting. |  | It is an ongoing challenge for nursing homes to keep COVID-19 out of their facilities, especially with mandate changes. With a increase in COVID-19 cases, nursing homes must continue to be vigilant in practicing safe visitation | HQI developed and shared with nursing homes a "Checklist of Best Practices to Keep COVID-19 Out of Nursing Homes. This resource can be found on the HQIN Resource Center www.hqin.org HQI developed and shared a Safe Visitation in Nursing Homes resource. This resource explains how victors can help to keep their family and friends in nursing homes safe in times of communicable disease, including vaccination. This resource can be found on the HQIN Resource Center www.hqin.org |  | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Based on the Qualtrics/CMS reporting criteria 35.1% of nursing homes are reporting >= 90% booster rates. |  |  |  | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | 31 | 19 | 19 | 25 |  |  |  |  | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15
|  | Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time | 30327 | 30419 | 30374 | 30867 | 31022
|  | Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time | 20755 | 20739 | 21055 | 21400 | 21887
|  | Residents COVID-19 Vaccine Booster Rate: | 68.44% | 68.18% | 69.32% | 69.33% | 70.55%
|  | % RIR since DCO Start: | 68.54% | 67.9% | 70.72% | 70.74% | 73.75%

## June 2022
QIN/QIO Name: Health Quality Innovators
Region: KS, MO, SC, VA
Assigned COR: Nicole Crenshaw
Topic Area |  | Questions to Drive Success | Week 1 06/01/22 - 06/07/22 | Week 2 06/08/22 - 06/14/22 | Week 3 06/15/22 - 06/21/22 | Week 4 06/22/22 - 06/28/22 | Week 5 | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | [5 empty] | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 0 | 0 | 0 | 0 | [5 empty] | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | 0 | 0 | 0 | 0 | [5 empty] | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | [5 empty] | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | Due to transitioning to monthly events, we are also now monitoring access to our online resources and recorded events. For 05/23/22 - 05/29/22 the top accessed resources are: 1) Safe Visitation - 28 unique views 2) Bulletin Board Bundles - 13 unique views 3) Booster Questions Poster & Handout - 5 unique views | Monthly Simple Strategies Standup held on 6/14/22 - "Don't Get Tagged: Be Prepared for a Staff Vaccination Survey" * 50 people registered and 28 nursing homes attended. Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 05/23/22 - 05/29/22 the top accessed resources are: 1) The Right View for CDC COVID-19 Data Tracer Learning Module - 15 unique views 2) Bulletin Board Bundles - 14 unique views 3) Resident Vaccine Administrator Form - 11 unique views | Monthly Prepare, Prevent, Protect educational series held on 6/21/22 - "Risk Assessment, Emergency Preparedness, Regulatory" 52 registered, 34 attended Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 06/12/22 - 06/19/22 the top accessed resources are: 1) Don't Get Tagged: Be Prepared For a Staff Vaccination Survey Slides - 37 unique views 2) COVID19 Vaccination Tracking Tool - 18 unique views 3) COVID-19 Booster Shots Flyer - 11 unique views | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 06/20/22 - 06/26/22 the top accessed resources are: 1) Checklist of Best Practices to Keep COVID-19 Out of a Nursing Home - 22 unique views 2) Risk Assessment Emergency Preparedness Regulatory Compliance - 14 unique views 3) COVID-19 Vaccine Tracker - 10 unique views | [5 empty] | Qualtrics - General Outreach - column EF
| 2c. | What is the duration of events and what relevant topics have been shared? | N/A | Session duration 30 minutes. Session Goals: 1) Assist attendees in gaining knowledge related to updates associates with COVID-1 vaccines and boosters 2) Assist attend in meeting CMS regulatory expectations | Session duration an hour. Session Goals: 1) Introduce and tutor audience in creation and implementation of infection prevention components essential to a robust infection prevention program 2) Collaborate with nursing home staff with an infection prevention role/duties to booster the facility's infection prevention program 3) Infection prevention risk assessment function 4) Emergency preparedness plan - infection prevention 5) Infection prevention program regulatory compliance | N/A | [5 empty] | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | [5 empty] | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | Direct consultation with 28 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers | Direct consultation with 5 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Public display of NH vaccination rates over time 3) Help develop vaccine champions as advocates and trusted messengers | Direct consultation with 45 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Coaching on motivational interviewing techniques 2) Provide vaccine safety and efficacy information from trusted sources 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers | Direct consultation with 13 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Coaching on motivational interviewing techniques 2) Provide vaccine safety and efficacy information from trusted sources 3) Public display of NH vaccination rates over time |  | As of 06/21/22, we have attempted to contact all referred nursing homes. (10) refusals have been documented as "refusing to participate" after being unresponsive to 5 or more attempts to contact or per facility leadership decision. |  |  |  | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. |  |  |  |  | Released new resource " The Right View for Nursing Homes: CDC COVID Data Tracker Learning Module. This is a brief video (3.5 minutes long) that walks through the current CDC COVID Data Tracer default setting and what to change to access the data nursing homes need. This resource can be found on the HQIN.org resource website. Released resource "Checklist Can Help Keep COVID-19 Out of Nursing Home" This checklist was designed to supplement CMS and CDC guidelines to keep residents, staff and visitors safe in nursing homes, including vaccination requirements and access. This resource can be found at www.HQIN.org/resource | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues |  | Based on the Qualtrics/CMS reporting criteria 35.8% of nursing homes are reporting >= 90% booster rates. |  |  |  | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | 28 | 33 | 82 | 13 | [5 empty] | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12
|  | Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time | 31165 | 30613 | 30528 | 30336
|  | Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time | 22109 | 21768 | 22245 | 22196
|  | Residents COVID-19 Vaccine Booster Rate: | 70.94% | 71.11% | 72.87% | 73.17%
|  | % RIR since DCO Start: | 74.64% | 75.05% | 79.38% | 80.12%

## July 2022
QIN/QIO Name: HQI
Region: KS, MO, SC, VA
Assigned COR: Nicole Crenshaw
Topic Area |  | Questions to Drive Success | Week 1 June 29 - July 5 | Week 2 July 6 - July 12 | Week 3 July 13 - July 19 | Week 4 July 20 - July 26 | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. |  |  |  |  | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 0 | 0 | 0 | 0 |  |  |  |  | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | 0 | 0 | 0 | 0 |  |  |  |  | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the weekly virtual events and shares updated guidance and resources |  |  |  |  | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 06/27/22 - 07/03/22 the top accessed resources are: 1) Checklist of Best Practices to Keep COVID-19 Out of a Nursing Home - 11 unique views 2) COVID-19 Booster Action Plan - 10 unique views 3) COVID-19 Vaccine Tracker - 10 unique views Simple Strategies Standup scheduled for July 12 and Prepare, Prevent, Protect session scheduled for July 19. | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 07/04/22 - 07/10/22 the top accessed resources are: 1) I Wear a Mask Because - 32 unique views 2) COVID-19 Bulleting Board Bundles - 11 unique views 3) COVID-19 Vaccine Tracker - 7 unique views 7/12/22 Simple Strategies Standup: CDC COVID Data Tracker - The Key to Determine the Frequency of Routine Staff Testing (84 registered/24 attendees) Prepare, Prevent, Protect session scheduled for July 19. | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 07/11/22 - 07/17/22 the top accessed resources are: 1) I Wear a Mask Because - 41 unique views 2) COVID-19 Data Tracker - Key to Determine Testing - 25 unique views 3) Staff Booster Action Plan - 8 unique views 7/19/22 Prepare, Prevent, Protect: Program Plan, Policies and Resources (75 registered/26 attendees) | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 07/18/22-7/24/22 the top accessed resources are: 1) Staff booster vaccine action plan - 39 unique views 2) Infection prevention program plan and policies - 24 unique views 3) I Wear a Mask Because poster - 17 unique views |  |  |  |  | Qualtrics - General Outreach - column EF
| 2c. | What is the duration of events and what relevant topics have been shared? | N/A | Simple Strategies Standup Duration - 45 minutes Topics: 1) Assist attendees in meeting CMS regulatory requirements for routine staff testing 2) Assist attendees in gaining knowledge related to the accurate use of the CDC COVID Data Tracker Website 3) Routine testing of staff vaccinated vs unvaccinated | Prepare, Prevent, Protect - 52 minutes Topics: 1) Infection prevention program Oversight 2) Infection prevention plan elements 3) Putting plans and policies into action | N/A |  |  |  |  | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse |  |  |  | A facility shared that they address vaccination status during each care plan meeting with the resident or their family/representative. The care plan meeting allows the staff the opportunity to address any concerns/questions that the resident or their family/representative may have regarding the vaccine. | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | Direct consultation with 17 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers | Direct consultation with 11 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers | Direct consultation with 17 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers 5) Promote public recognition of individual staff vaccination status 6) Shared templates to help create information board or website about vaccination | Direct consultation with 20 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers 5) Promote public recognition of individual staff vaccination status 6) Shared templates to help create information board or website about vaccination | As of 07/26/22, we have attempted to contact all referred nursing homes. (11) refusals have been documented as "refusing to participate" after being unresponsive to 5 or more attempts to contact or per facility leadership decision. |  |  |  | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. |  |  |  | Developed "I Wear a Mask Poster" to normalize mask use even the environment of vaccine use. | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Based on the Qualtrics/CMS reporting criteria 36.3% of nursing homes are reporting >= 90% booster rates. |  |  |  | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | 17 | 37 | 33 | 20 |  |  |  |  | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2022-06-19 | 2022-06-26 | 2022-07-03 | 2022-07-10
|  | Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time | 30834 | 31041 | 31036 | 30851
|  | Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time | 22992 | 23178 | 23208 | 23328
|  | Residents COVID-19 Vaccine Booster Rate: | 74.57% | 74.67% | 74.78% | 75.62%
|  | % RIR since DCO Start: | 83.3% | 83.55% | 83.82% | 85.88%

## August 2022
QIN/QIO Name: Health Quality Innovators (HQI)
Region: KS, MO, SC, VA
Assigned COR: Nicole Crenshaw
Topic Area |  | Questions to Drive Success | Week 1 Jul 27 - Aug 02 | Week 2 Aug 03 - Aug 09 | Week 3 Aug 10 - Aug 16 | Week 4 Aug 17 - Aug 23 | Week 5 Aug 24 - Aug 30 | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. |  |  |  |  | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the virtual events and shares updated guidance and resources Develop Vaccine Champion Social Media Package and promotional messaging to share with stakeholders Booster Blitz Strategy (8/1/22 - 8/12/22): Request co-branding of TMF infographic “Who Stays Well After Direct Exposure to COIVD-19” and utilize as an easy at a glance poster to share vaccination statistics. (Completed) Develop “Why Get Boosted Now” commercial and messaging to promote the administration of boosters now as opposed to waiting until the fall. (Completed) Develop messaging “Where are You in the Scope of Vaccination” to help individuals understand the need for a vaccination and where they are in the timeframe for the booster vaccine. Release Vaccine Champion Social Media Package; “Why Get Boosted Now” commercial with messaging and “Where are You in the Scope of Vaccination” messing via Weekly Dose and HQI social medica platforms (Completed) | Booster Blitz Strategy (8/1/22 - 8/12/22): Distributing the following resources via the August 11 edition of the Weekly Dose and HQI social media platforms: 1) Who Stays Well After Direct Exposure to COIVD-19 infographic 2) Why Wait? Vaccines Can Keep Us Healthy and Is It Time to Get Your Booster videos. Both videos are under two minutes and packaged to shown in common spaces and shared through electronic communication with staff, residents and families. Under development is messaging “Where are You in the Scope of Vaccination” to help individuals understand the need for a vaccination and where they are in the timeframe for the booster vaccine. | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the virtual events and shares updated guidance and resources Two week Booster Blitz completed | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the virtual events and shares updated guidance and resources | "Where are You in Scope of Vaccination" continues to be in development |  |  |  | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 07/25/22-7/31/22 the top accessed resources are: 1) Bulletin board bundles - 28 unique views 2) Vaccine Champion Social Media Package - 13 unique views 3) COVID-19 vaccine letter to residents/families - 11 unique views 4) What is long COVID - 11 unique views 5) COVID-19 staff booster action plan - 10 unique views | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 08/01/22 - 08/07/22 the top accessed resources are: 1) Vaccine champion social media package - 117 unique views 2) What is long COVID - 23 unique views 3) COVID-19 provider letter to residents and families - 8 unique views Simple Strategies Standup: Vital Vaccines - Highlighting the Important Role of Vaccines and Vaccine Champions in Wellness (106 registered/19 attendees) | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 08/08/22 - 08/14/22 the top accessed resources are: 1) COVID-19 infographic poster - 120 unique views 2) Vaccine champion social media package - 107 unique views 3) Vaccines highlighting the important role of vaccines and vaccine champions - 19 unique views Prepare, Prevent, Project: Compliance Monitoring, Analysis and Feedback (registered 103, attended 29) | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 08/08/22 - 08/14/22 the top accessed resources are: 1) COVID-19 infographic poster - 113 unique views 2) Compliance and Monitoring presentation - 27 unique views 3) I Wear a Mask & I Got Boosted - 20 unique views 4) Vaccine Champion Social Media Package - 20 unique views 5) Booster Question Poster/Handout - 18 unique views | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 08/08/22 - 08/14/22 the top accessed resources are: 1) COVID-19 infographic poster - 38 unique views 2) I Wear a Mask & I Got Boosted - 32 unique views 3) Sample PHE Preparedness Plan - 22 |  |  |  |  | Qualtrics - General Outreach - column EF
| 2c. | What is the duration of events and what relevant topics have been shared? | N/A | Simple Strategies Standup Objectives (50 minutes) 1) Review vaccines for people living in nursing homes 2) Apply updated knowledge to plan for co-administrating vaccinations during booster clinics 3) Utilize case studies to review the benefits of the COIVD-19 booster and other vaccinations for staff and residents of nursing homes | Prepare, Prevent, Project Objectives (49 minutes duration) 1) Competency-based training 2) Auditing processes and tools 3) Strategies for improving compliance | N/A | N/A |  |  |  |  | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse HQI will prioritize the "no contact" list provided on July 27as part of the Booster Blitz (8/1/22 - 8/12/22) | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse HQI will prioritize the "no contact" list provided on July 27as part of the Booster Blitz (8/1/22 - 8/12/22) | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse HQI prioritized the "no contact" list provided on July 27as part of the Booster Blitz (8/1/22 - 8/12/22) | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Analysis of “no contact/refusal” list revealed six nursing homes are closed. During the Booster Blitz we achieved 100% outreach. And we completed Qualtrics questionnaires for 65.15% of the facilities on the list. As of 8/30/22 outreach for all referrals has been completed. 53 nursing home are pending contact. |  |  |  | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | Direct consultation with 20 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers 5) Promote public recognition of individual staff vaccination status 6) Shared templates to help create information board or website about vaccination 7) NHSN data support | Direct consultation with 19 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers 5) Promote public recognition of individual staff vaccination status 6) Shared templates to help create information board or website about vaccination 7) NHSN data support | Direct consultation with 39 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers 5) Promote public recognition of individual staff vaccination status 6) NHSN data support | Direct consultation with 21 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers 5) Promote public recognition of individual staff vaccination status 6) NHSN data support | Direct consultation with 9 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers 5) Promote public recognition of individual staff vaccination status 6) NHSN data support |  |  |  |  | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. Partner with stakeholders to promote Booster Blitz messaging to include trade associations, state health departments, AMDA - The Society for Post Acute Care and LTC Medicine, Quality Improvement Program for Missouri (QIPMO) (8/1/22 - 8/12/22) State trade associations and health departments will utilize HQI messaging and toolkits to promote vaccination and boosters via list servs and newsletters. Develop messaging that the AMDA – The Society for Post-Acute and Long Term Care Medicine state chapters can utilize to promote the use of the HQI COVID-19 Letter to Residents and Family Members by attending physicians. Share messaging and materials with AMDA state chapters. Investigate opportunities to be included on the agenda with upcoming state trade associations and health departments events. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. Partner with stakeholders to promote Booster Blitz messaging to include trade associations, state health departments, Quality Improvement Program for Missouri (QIPMO) (8/1/22 - 8/12/22). Messaging for week of August 8 includes the following: 1) Who Stays Well After Direct Exposure to COIVD-19 infographic 2) Why Wait? Vaccines Can Keep Us Healthy and Is It Time to Get Your Booster videos. Both videos are under two minutes and packaged to shown in common spaces and shared through electronic communication with staff, residents and families. The Centers for Disease Control and Prevention (CDC) recently approved the Advisory Committee on Immunization Practices (ACIP) recommendation for the NOVAVAX COVID-19 vaccine, named NVX-CoV2373. HQIN's New COVID-19 Vaccine Under Emergency Use Authorization Flyer will be distributed via the August 11 Weekly Dose. The flyer lists key considerations for the Novavax COVID-19 vaccine as well as additional reference links. Refer to it for an overview of vaccine ingredients, recommended dosing as well as approved age requirements. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | 8/2/22 - Virginia Health Department (VDH) Long Term Care Advisory Call – On agenda to promote QIN-QIO assistance and resources to help increase vaccination and booster rates. Partners shared updated messaging and new resources during the Booster Blitz time period via newsletters and list servs. 8/12/22 Leading Age Kansas promoted HQIN Booster Blitz resources during a members call. HQIN vaccine/booster consultation will be provided and resources promoted during upcoming trade association conferences: 8/17 - 8/18 Kansas Adult Care Executives (KACE) annual conference 8/28 - 8/31 9/28 - 9/30 Kansas Health Care Association (KHCA) annual conference and trade show 9/13 - Virginia Health Care Association (VHCA) annual conference and trade show |  |  |  | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Based on the Qualtrics/CMS reporting criteria 34.8% of nursing homes are reporting >= 90% booster rates. |  |  |  | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | 26 | 38 | 68 | 21 | 9 |  |  |  |  | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2022-07-17 | 2022-07-24 | 2022-07-31 | 2022-08-07 | 2022-08-14
|  | Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time | 25900 | 26170 | 26767 | 27956 | 27651
|  | Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time | 19939 | 20186 | 20478 | 21326 | 21057
|  | Residents COVID-19 Vaccine Booster Rate: | 76.98% | 77.13% | 76.5% | 76.28% | 76.15%
|  | % RIR since DCO Start: | 89.25% | 86.21% | 84.69% | 82.76% | 82.08%

## September 2022
QIN/QIO Name: HQI
Region: KS, MO, SC, VA
Assigned COR: Nicole Crenshaw
Topic Area |  | Questions to Drive Success | Week 1 Aug 30 - Sept 6 | Week 2 Sept 7 - Sept 13 | Week 3 Sept 14 - Sept 20 | Week 4 | Week 5 | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | Ongoing assessment of needs via direct nursing home outreach and via needs assessment. | [6 empty] | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 0 | 0 | 0 | [6 empty] | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | 0 | 0 | 0 | [6 empty] | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the virtual events and shares updated guidance and resources | Distributing a weekly e-bulletin "The Weekly Dose" which promotes the virtual events and shares updated guidance and resources | [6 empty] | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 08/29/22 - 09/04/22 the top accessed resources are: 1) Sample Public Health Emergency Preparedness Plan - 14 unique views 2) Direct exposure to COVID 19 Infographic - 13 unique views 3) COVID-19 booster videos - 8 unique views 4) Vaccine Champion Social Media Package - 8 unique views | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 09/05/22 - 09/11/22 the top accessed resources are: 1) I wear a mask - 36 unique views 2) Direct exposure infographic poster - 17 unique views 3) Staff exposure/prevention action plan template - 11 unique views 4) Vaccine champion social media package - 10 unique views Simple Strategies Standup held on 9/13/22 (webinar): 123 registrants, 31 attendees) | Due to transition to monthly events, we are also now monitoring access to our online resources and recorded events. For 09/12/22 - 09/18/22 the top accessed resources are: 1) COVID-19 signage - 56 unique views 2) "I Wear a Mask Because" - 27 unique views 3) Mining for Motivation - 26 unique views Prepare, Prevent, Protect held on 9/20/22 (webinar): 126 registrants, 43 attendees) | [6 empty] | Qualtrics - General Outreach - column EF
| 2c. | What is the duration of events and what relevant topics have been shared? | N/A | Simple Strategies Standup: Mining for Motivation - Finding Other's Internal Motivation with Person-Centered Interviewing (53 minutes) Objectives: 1) Discuss resource and principles for motivational interviewing for patient/caregiver communication 2) Review benefits of person-centered interviewing 3) Observe a plan for honoring autonomy 4) Apply updated knowledge to motivational interviewing to improve vaccination uptake | Prepare, Prevent, Protect: Lab Services, Epidemiology, Surveillance, Outbreak Investigation (39 minutes) Objectives: 1) Improve patient care through infection prevention collaboration with laboratory services 2) Utilize epidemiology principles 3) Understand the elements of surveillance 4) How to conduct outbreak investigation | [6 empty] | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | Administrator, DON and Infection Prevention Nurse are included in virtual event invitations and receive "Weekly Dose" e-bulletin Direct TA includes the Administrator, DON and/or Infection Prevention Nurse | [6 empty] | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | Direct consultation with 15 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers 5) Promote public recognition of individual staff vaccination status 6) NHSN data support | Direct consultation with 6 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers 5) Promote public recognition of individual staff vaccination status 6) NHSN data support | Direct consultation with 34 leaders to assess vaccination program and conduct RCA for identified gaps. Including: 1) Vaccine safety and efficacy information from trusted sources 2) Coaching on motivational interviewing techniques 3) Public display of NH vaccination rates over time 4) Help develop vaccine champions as advocates and trusted messengers 5) Promote public recognition of individual staff vaccination status 6) NHSN data support |  |  | As of 9/20/22 outreach for all referrals has been completed and 54 nursing home are pending contact. |  |  |  | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | Provided guidance during 1:1 consultation utilizing CDC COVID-19 Vaccine and Booster resources. | [6 empty] | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues | Utilization of HQI dashboard and facility reports and NHSN data continues |  |  | Based on the Qualtrics/CMS reporting criteria 35% of nursing homes are reporting >= 90% booster rates. | Booster rates have begun to plateau. During TA, nursing homes are reporting that they have "paused" booster vaccination due to the pending release of the new bivalent vaccine. In addition, nursing homes are sharing that they have no access to booster vaccines as pharmacies are no longer supplying original mRNA vaccines and have not yet received the new bivalent vaccine. As reference, the FDA issued the following statement on August 31: With FDA’s authorization, the monovalent mRNA COVID-19 vaccines are not authorized as booster doses for individuals 12 years of age and older. Appointments for individuals 12 years of age and older for previously-authorized monovalent Pfizer-BioNTech or Moderna boosters need to be rescheduled for when locations have the bivalent COVID-19 vaccines available. https://www.fda.gov/emergency-preparedness-and-response/coronavirus-disease-2019-covid-19/covid-19-bivalent-vaccine-boosters We are recommending nursing homes use this time to obtain consents and setup a process for vaccine clinics when the bivalent vaccine is available. We are also staying in contact with the state health departments to monitor availability of the new booster vaccine. |  |  | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | 15 | 37 | 77 | [6 empty] | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2022-08-21 | 2022-08-28 | 2022-09-04 | 2022-09-11
|  | Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time | 33189 | 28189 | 28768
|  | Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time | 25766 | 21946 | 22494
|  | Residents COVID-19 Vaccine Booster Rate: | 77.63% | 77.85% | 78.19%
|  | % RIR since DCO Start: | 82.28% | 82.8% | 83.95%

## October 2022
QIN/QIO Name:
Region:
Assigned COR:
Date:
Topic Area |  | Questions to Drive Success | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | [9 empty] | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 2 | 1 | [7 empty] | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | [9 empty] | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | [9 empty] | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | [9 empty] | Qualtrics - General Outreach - column EF
| 2c. | What is the duration of events and what relevant topics have been shared? | [9 empty] | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | [9 empty] | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | [9 empty] | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | [9 empty] | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | [9 empty] | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | [9 empty] | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09
Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time
Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time
Residents COVID-19 Vaccine Booster Rate:
% RIR since DCO Start:

## November 2022
QIN/QIO Name:
Region:
Assigned COR:
Date:
Topic Area |  | Questions to Drive Success | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | [9 empty] | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 2 | 1 | [7 empty] | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | [9 empty] | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | [9 empty] | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | [9 empty] | Qualtrics - General Outreach - column EF
| 2c. | What is the duration of events and what relevant topics have been shared? | [9 empty] | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | [9 empty] | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | [9 empty] | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | [9 empty] | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | [9 empty] | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | [9 empty] | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13
Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time
Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time
Residents COVID-19 Vaccine Booster Rate:
% RIR since DCO Start:

## December 2022
QIN/QIO Name:
Region:
Assigned COR:
Date:
Topic Area |  | Questions to Drive Success | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Progress/Status Updates | Challenges/Barriers | QIO Plans to Mitigate: Challenges/Barriers | Best Practices & Lessons Learned | Data Source
Coordination | 1a. | What actions have been taken to-date, to rapidly coordinate mobile/onsite vaccine clinics, designed to provide vaccines to NH residents and staff? | [9 empty] | Team - Implementation Plan
| 1b. | How many clinics have been coordinated for NH participation? | 2 | 1 | [7 empty] | Qualtrics - column EI
| 1c. | How many residents and staff have received COVID vaccinations or boosters from the clinics to-date? | [9 empty] | Qualtrics - column EJ and EK
Educational Campaign | 2a. | What actions have been taken to-date to establish an aggressive educational campaign, which partners with the CDC, across ~ 4000 NH, (including weekly distribution of training resources, conducting webinars, and clinician office hours)? | [9 empty] | Qualtrics - Topic, Resources from webinar/office hours
| 2b. | What has been the quantitative reach of the QIN’s educational campaign, including the mode of engagement | [9 empty] | Qualtrics - General Outreach - column EF
| 2c. | What is the duration of events and what relevant topics have been shared? | [9 empty] | Qualtrics - General Outreach - column EE
Leadership | 3a | What actions have been taken to-date to directly contact NH leadership to jointly develop a plan to address issues with vaccine uptake? | [9 empty] | Implementation Plan - General Outreach and Technical Assistance
| 3b | What is the number of NHs with whom QIN-QIO leadership is actively collaborating with nursing homes to address specific issues with vaccine uptake? | [9 empty] | Qualtrics - Referrals with an encounter plus General Outreach count
Booster Rates | 4a | What actions have been taken to-date to prepare nursing homes to adapt to an evolving pandemic situation and address emerging guidance (as convener) from federal and state health departments related to boosters and vaccines? | [9 empty] | Team - Vaccine Activities SharePoint list (cumulative)
| 4b | What are the QIN’s current activities to monitor and report COVID booster rates based on eligibility? | [9 empty] | Technical Assistance and data captured through monthly self-reporting. Eventually, NHSN.
| 4c | What is the number of NHs who receive support from the QIO to update or clarify guidance and regulation on vaccinations and boosters? | [9 empty] | Qualtrics - column EL
Reporting from NHSN as of week ending:
|  | Residents Booster Rate Tracking | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18
Denominator: Number of Residents Staying in this Facility for At Least 1 Day This Week who Received a Completed COVID-19 Vaccination at Any Time
Numerator: Number of Residents with a Completed Vaccination Staying in this Facility for At Least 1 Day This Week who Received a COVID-19 Vaccine Booster at Any Time
Residents COVID-19 Vaccine Booster Rate:
% RIR since DCO Start: