## Task B.2 (hidden)
Goal | Task | Action | Start | Finish | Status | Personnel Resources | Notes
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
|  | Contact referrals sources such as hospitals, pharmacies, providers, community organizations and partners/stakeholders who interface with the target population. | 2016-01-04 | 2019-07-14 | Ongoing | Improvement Consultant, Communications
| Develop community partner relationships | Meet with community organizations (ex. faith-based organizations, senior nutrition sites, grocery stores, fraternal organizations, beauty and barber shops) highlighted by the environmental scans to develop opportunities to initiate and/or increase DSME workshops in these areas. | 2016-01-04 | 2019-07-14 | Ongoing | Improvement Consultant
|  | Participate in partner advisory groups that align with EDC | 2014-08-01 | 2019-07-14 | Ongoing | Program Manager, Improvement Consultant
| Develop HQI led workshops | Assess all opportunities for sustainable practice by collaborating with existing partners | 2015-10-01 | 2019-07-14 | Ongoing | Improvement Consultant
|  | Training new partners, or providing HQI led workshop. | 2015-08-01 | 2019-07-14 | Ongoing | Improvement Consultant
|  | Review HQI training resources | 2014-08-01 | 2019-05-01 | Ongoing | Program Manager, Improvement Consultant | Master trainers, peer leader. New process for organizing leader trainings in CRM
|  | Develop and implement action plan when measures are inadequate. | 2015-07-01 | 2019-07-14 | In process | Improvement Consultant | New action plan developed and implemented 7/17 - 10/17
Conducting workshops for DSME
| Establish workshop expectations (Subcontractor) | Review Workshop Reference Guide | 2016-01-04 | 2016-02-29 | Completed | Improvement Consultant
|  | Set up weekly meetings | 2016-11-01 | 2016-11-30 | Complete | Improvement Consultant | Standard agenda of topics - now meeting Bi weekly in MD and montly in VA
|  | Gather required documentation | 2015-08-01 | 2019-06-30 | Ongoing | Improvement Consultant | Participant Packet
| Establish workshop expectations (Community Partner) | Review Workshop Reference Guide | 2016-02-01 | 2019-05-01 | In process | Improvement Consultant | Initial meetings complete. Future meetings will be scheduled as needed. Note - MOAs being updated 10/17
| Assessment of workshop capacity | Review trainer and workshop capacity | 2016-02-01 | 2016-03-31 | Completed | Program Manager, Improvement Consultant | For all entities conducting workshops
| Provide fidelity visits | Create system for tracking and documentation of fidelity visits | 2016-02-01 | 2019-06-30 | In process | Improvement Consultant, Lean Six Sigma Manager, Analytics | For Community Partners, Virginia AAA, and HQI led workshops. - Currently DARS is assuming this role, with assistance by HQI where needed in VA
| Monitor workshop schedule | Create system for tracking workshops being facilitated by subcontractor and/or community partners | 2015-10-01 | 2015-12-31 | Completed | Improvement Consultant
|  | Track CIQIP measures | 2016-01-01 | 2019-07-14 | Ongoing | Improvement Consultant | Reviewing bi-weekly at team meetings. Dashboard of measures available.
|  | Established process measures for # of workshops completing the current quarter and next quarter | 2016-02-01 | 2016-02-28 | Completed | Program Manager, Improvement Consultant, Lean Six Sigma Manager
|  | Review opportunities for additional workshops if too few are scheduled | 2015-05-01 | 2019-05-01 | Ongoing | Program Manager, Improvement Consultant
Recruiting qualified beneficiaries
| Develop community/stakeholder referral sources (beneficiaries) | Contact local Pharmacies, churches, other community group as workshops are developed to help publicize | 2014-08-01 | 2019-05-01 | Ongoing | Improvement Consultant | targeting senior low-income housing in MD as well.
| Develop physician referral sources | Contact local Physicians as workshops are developed to help publicize | 2014-08-01 | 2019-05-01 | Ongoing | Improvement Consultant | Initiating involvement with MDPCP
| Utilizing targeted marketing material | Utilize targeted marketing material | 2014-08-01 | 2019-05-01 | Ongoing | Communications Manager | Initiated FB test 3/2019 for SSEEVA
| Patient and Family Council | Utilize patient and family advisory council to provide input/guidance communication channels to increase the number of qualified beneficiaries | 2016-07-01 | 2019-05-01 | Ongoing | Program Integration Mgr, Program Manager, Patient Family Council, Communications | Discussing/reviewing marketing ideas with PFAC during October 2017 meeting.
Recruit Providers
| Identify physicians/practices eligible for recruitment | Utilize CMS data to target practices including PQRS reports | 2014-08-01 | 2017-07-31 | complete | Program Manager, Analytics | Note - recruitment is now in maintenance mode,
| Align and prioritize physician recruitment with workshop availability | Overlap targeted practices with workshop availability | 2014-08-01 | 2017-07-31 | complete | Program Manager, Improvement Consultant, Analytics | Note - recruitment is now in maintenance mode,
| Stakeholder assistance with recruitment | Request stakeholders such as MedChi and the Medical Society of Virginia promote importance of programs and physician participation. Also identify stakeholders at the local level, such as the Richmond Academy of Medicine, to assist. | 2014-08-01 | 2017-07-31 | complete | IDIQ Director, Improvement Consultant | Note - recruitment is now in maintenance mode,
| Identify alignment opportunities with other tasks | Set up cross task meeting to identify alignment opportunities (semi annually) | 2014-08-01 | 2017-07-31 | complete | Project Integration Manager | Align with Care Transitions activities. Discuss referrals by pharmacies, discuss pharmacies providing workshops or becoming diabetes centers.
| Subcontractor recruitment efforts | MD - Continue to work with MedChi in Maryland to recruit targeted providers | 2015-04-01 | 2017-07-31 | completed | Program Manager | Note - recruitment is now in maintenance mode, no longer utilizing Med Chi in Maryland
| Medical Society recruitment efforts | VA -Establish relationship with MSV | 2016-02-01 | 2017-07-31 | completed | Program Manager | Note - recruitment is now in maintenance mode,
| Evaluate overlap with other task area | Conduct practice profile assessments | 2015-08-01 | 2017-07-31 | completed | Improvement Consultant | Note - recruitment is now in maintenance mode,
| Ensure that providers have access to current evidence-based practice guidelines | Provide current evidence-based practice guidelines on the online community and invite providers to join. Educate on use of tools and resources for both providers and patients. Push out evidence-based practice guidelines to participating practices | 2015-10-01 | 2019-07-14 | Ongoing | Improvement Consultant, Communications | Content has been provided in mailings, visits and eNewsletters
|  | Educate Providers to leverage EHR to identify patients with diabetes and prediabetes for DSME workshops | 2016-02-01 | 2019-07-14 | In process | Improvement Consultant
Sustainability
| Collaborate with CFE to achieve and exceed targets for qualified completers in Maryland | Work with CFE to create structure of adding more workshops and Peer Leader training events | 2016-01-04 | 2016-07-31 | completed | Program Manager, Improvement Consultant
| Collaborate with DARS to spread DSME workshops offered in VA | DARS-Negotiate and sign a subcontract agreement with DARS to provide a structure to increase DSME workshops provided by AAAs in VA | 2015-11-01 | 2016-03-31 | Completed | Population Health Director | Note - have supported DARS with funing opps
| Ensure adequate Stanford trainers and peer leaders to conduct trainings and workshops | Conduct assessment of Stanford master trainers and peer leaders at least annually | 2016-01-04 | 2019-01-31 | Ongoing | Program Manager, Improvement Consultant | required annually as SMRC license
|  | Training additional Master Trainers | 2016-03-01 | 2016-06-30 | In process | Improvement Consultant | Completed one MT. Currently working with VDH to schedule one additonal MT prior to end of contract.
|  | Develop a plan to address identified training needs to fill gaps and/or increase capacity | 2016-01-04 | 2019-01-31 | Ongoing | Program Manager, Improvement Consultant | HQI MTs actively provide LTs where needed.
| Collaborate with community partners to ensure they are continuing to schedule DSME workshops and they are reaching the target population | Contact community partners on a monthly basis to assess workshop planning/scheduling and identify/address issues they are encountering | 2015-10-01 | 2019-05-01 | Ongoing | Improvement Consultant
|  | Monitor community partner's ability to effectively recruit and retain the target populations. Brainstorm recruitment ideas, provide toolkits and resources and customize to their particular needs. | 2016-01-04 | 2019-05-01 | Ongoing | Improvement Consultant
| Meet at least annually with key stakeholders to review diabetes education goals, targets, milestones and new opportunities to partner and align efforts | Annual meeting with the Department of Health and Mental Hygiene, Office of Minority Health, Maryland Rural Health Foundation, American Diabetes Association | 2016-01-04 | 2016-12-31 | Ongoing | Program Manager, Improvement Consultant
| Increase the numbers of diabetes educators and certified diabetes centers | Collaborate with stakeholders to promote and encourage the continued training of diabetes educators (both CDEs and CHWs) and to increase the number of certified diabetes centers | 2014-08-01 | 2019-07-14 | Ongoing | Program Manager, Improvement Consultant. | Active participation on CHW AG in VA; Additonal chw groups in MD as well; Also active member of VDC. Promoted Mary Ann Hodorowicz TA opportunity
Lower Extremity Amputation Rates
| Raise awareness of LE amputations in patients with diabetes | Analyze data by state to determine facilities/geographic areas with highest rates of LE amputation | 2016-01-11 | 2016-02-29 | Completed | Program Manager, Improvement Consultant, Analytics
|  | Collaborate with Care Transitions to raise community awareness in areas with highest rates. | 2016-03-01 | 2019-03-31 | Ongoing | Program Manager, Care Transitions Director
|  | Compare data to environmental scan for ADA recognized diabetes centers and CDEs to identify target areas for increased focus | 2016-03-01 | 2016-12-31 | Completed | Program Manager, Improvement Consultant, Analytics | Will revisit as new data is available
|  | Utilize data to target areas for workshop development | 2016-03-01 | 2017-03-01 | Completed | Program Manager, Improvement Consultant | Will revisit as new data is available

## Task B.4 (hidden)
Consolidated in Task D.1 per Modification 4
| Activity (detailed description of activities necessary to complete each task) | Start | Finish | Status | Personnel Resources | Notes
B.4.2 Provider and Practitioner Recruitment
| Utilize data sources to identify number of providers and practitioners to participate in QIN-QIO direct technical assistance and LAN activities. Identified providers and practitioners to include Eligible hospitals and Critical Access Hospitals (CAHs) with installed ONC certified CEHRT. | 2014-08-01 | 2014-08-22 | Completed | Improvement Consultant | There are no CAHs in Maryland
| Develop and maintain recruitment database with contact information and history of encounters. | 2014-09-15 | 2019-07-31 | Ongoing | Improvement Consultant, IT staff
| Obtain list from VHIT and CRISP for physician practices with contact information to target recruitment. | 2014-08-01 | 2014-08-22 | Completed | Improvement Consultant
| Collaborate with local stakeholder/partners to promote QIN activities and aid in recruitment to members, such as the state Medical Group Management Associations, Academies of Family Physicians, Areas Agency on Aging, etc. | 2014-08-01 | 2019-07-31 | Ongoing | IDIQ Director, Improvement Consultant, Communications
| Develop high level SOW fact sheets for the MU of HIT to explain program requirements and goals/benefits of joining the network. | 2014-08-01 | 2014-09-08 | Completed | Improvement Consultant, Communications
| Coordinate and facilitate a kick off webinar to discuss project goals and gain interest in joining network. | 2014-09-01 | 2014-10-02 | Completed | Improvement Consultant
| Send out participation agreement to interested participants and obtain signatures for participation in network via hardcopy and electronic submission. | 2014-10-20 | 2019-07-31 | Ongoing | Improvement Consultant, Communications
| Send introductory letter/email with follow up phone call to answer specific questions, review participation requirements and gain commitment for participation and active engagement. | 2014-10-20 | 2019-07-31 | Ongoing | Improvement Consultant, Communications | As needed.
| Identify areas of needs and discuss solutions during internal weekly team meetings to increase and maintain recruitment numbers throughout the project. | 2014-08-01 | 2019-07-31 | Ongoing | Task Leads, Improvement Consultant
B.4.3 Beneficiary and Family Engagement
| Research patient advocacy groups and patient family engagement advisory councils to identify potential beneficiaries/representatives to participate in VHQC Patient and Family Council. | 2014-08-01 | 2019-03-31 | Ongoing | Improvement Consultant | Actively recruiting for MD advisors. Working with various stakeholders such as AARP, American Heart Association and the AAA for assistance with recruitment.
| Engage patients that have signed up via Volunteer Interest Form and have expressed an interest in HIT, Meaningful Use and/or payment models per the process established by the VHQC Patient and Family planning committee. | 2015-02-01 | 2016-07-31 | Completed, but work and additional recruitment ongoing | Improvement Consultant, Communications | The Patient and Family Advisory Council is up and running with participants engaged from both states. A regular schedule of meetings and calls has been developed.
| Scan the environment for resources that promote health literacy, patient and family engagement, and encourage use of HIT (i.e. patient portals) to share with beneficiaries and/or family members. | 2014-10-13 | 2019-07-31 | Ongoing | Improvement Consultant
| Involve patients and caregivers in the development and implementation of education/teaching tools/registration forms/clinic signage/process for scheduling appointments/website content so materials are written or available in formats that are understandable and useful to all people, regardless of their level of literacy. | 2015-05-04 | 2019-07-31 | Ongoing | Improvement Consultant | Advisors received orientation at end of April. Subsequent Council meetings discussed Population Health activities in further detail.
| Develop application form that potential beneficiaries and patient advocates will complete. | 2015-02-01 | 2015-03-31 | Completed | Improvement Consultant, Communications
| Invite families and patients to serve as advisors on the VHQC Patient and Family Council. As advisors they will support region wide healthcare improvement initiatives that focus on reducing cardiac disparities | 2015-08-31 | 2019-07-31 | Ongoing | State Program Director, Improvement Consultant, Communications, Project Assistant, VHQC Patient and Family Council planning committee | Currently have 6 Advisors in VA. Ongoing recruitment efforts in MD.
B.4.4 Partner and Stakeholder Recruitment and Collaboration
| Research state chapters or regional associations and societies to obtain contact info for potential recruitment, such as HIMSS, Medical Societies and other professional organizations (whom will help VHQC promote HIT initiative). | 2014-08-01 | 2014-08-22 | Completed | Improvement Consultant
| Establish structure of Advisory Committee meetings and identify members for the Advisory Committee. | 2014-10-13 | 2014-12-31 | Completed | Improvement Consultant | Coordinated with D1
| Contact potential Advisory Committee members via email or phone, including relevant stakeholder organizations such as RECs, HIEs, Medical Society, HIMSS, HFMA, etc. | 2014-10-20 | 2014-12-31 | Completed | Improvement Consultant, Clinical Innovation Officer | Coordinated with D1
| Develop and send invitation to join Advisory Committee member kick off meeting. | 2014-12-05 | 2015-01-23 | Completed | Improvement Consultant, Communications
| Coordinate and facilitate Advisory Committee Kickoff Meeting. | 2014-12-02 | 2015-01-23 | Completed | Improvement Consultant,
| Identify a target number of stakeholders/partners to recruit. | 2014-08-01 | 2014-08-22 | Completed | Improvement Consultant | Goal is to recruit minimum 5 stakeholder organizations throughout the contract.
| Meet with state REC (VHIT for VA and CRISP for MD) to discuss collaboration, co-branding webinars, and partnership opportunities; establish recurring opportunities to share happenings of each organization, such as attending staff meetings. | 2014-10-03 | 2019-07-31 | Ongoing | Improvement Consultant, VHIT | Actively partnering with RECs in MD and VA for LAN activities.
B.4.5 Provider Technical Assistance
| Organize EHR-specific user groups with vendor representatives and invite EPs to participate on calls to discuss EHR issues, such as reporting capabilities for prevention measures, Meaningful Use, patient portals, and workflows. | 2015-04-01 | 2019-07-31 | Ongoing | Improvement Consultant | There is a broad spectrum of EHRs represented by our Maryland providers, we are using materials gathered and/or created by the NCC or from our internal Physician Services staff.
| Provide instructions on running Meaningful Use reports from EHR and develop tip sheets/resources as needed. | 2015-10-01 | 2019-07-31 | In process | Improvement Consultant | Physicians Services offers tools and resources to providers. CMS resources and tools are also sent to providers. Physicians Services is also a resource itself as many coordinators can assist with vendor specific information.
| Gather Meaningful Use measures from participating EPs, EHs, CAHs to identify high performing provider mentors willing to share best practices and present on future webinars. | 2015-04-01 | 2019-07-31 | Ongoing | Improvement Consultant | Now that Meaningful Use 2015 is complete, we have been able to attain MU CQM reports and are in the process of analyzing which providers are top performers.
| Collect best practices for Meaningful Use (successful strategies) from high-performing EPs, EHs and CAHs and invite high-performer to present at LAN webinar. | 2015-08-01 | 2019-07-31 | Ongoing | Improvement Consultant | We continue to seek out high performing EP's to participate and share best practices.
| Scan the environment for Meaningful Use resources (fact sheets, toolkits, etc.) available from national and local partners/stakeholders and QIN NCC to create Meaningful Use Toolkit for participating EPs/EHs. | 2014-10-23 | 2019-07-31 | Ongoing | Improvement Consultant | Fact sheets and resources are available from Physicians Services. New fact sheets and online information will be developed when MACRA regulations are final.
| Develop resource repository accessible on VHQC's website for educational materials, webinar recordings, etc. | 2015-01-26 | 2019-07-31 | In process | Improvement Consultant, Communications | Online community launched. Team working to further develop our website, including links to webinars & educational -materials. Prerecorded modules have been uploaded and will be added to website as developed.
| Create dedicated email address for LAN participants to submit questions for technical assistance for MU. | 2014-09-11 | 2014-09-11 | Completed | Improvement Consultant, IT staff
| Conduct open door forums /office hours where participants may call in with questions and share ideas on related topics as needed. | 2015-02-09 | 2019-07-31 | Ongoing | Improvement Consultant | In addition to traditional format of webinars and online materials, held several online "office hours" prior to 2016 PQRS & MU submission, which were very successful. Plan to continue these in the future.
B.4.6 Learning and Action Networks
| Develop a branding name for LAN. | 2014-08-01 | 2014-09-29 | Completed | Improvement Consultant, , Communications | LANs now integrated across all Physician Focused tasks.
| Identify and discuss cross-cutting events with Advisory Committee members for co-branding and participation. | 2015-01-23 | 2019-07-31 | Ongoing | Improvement Consultant,
| Develop curriculum and schedule for quarterly LAN meetings that would include the learning system intervention packages from the QIN NCC. | 2015-01-01 | 2019-07-31 | Ongoing
| Develop co-branded templates for LAN materials and presentations for educational sessions with partners and stakeholders. | 2015-01-01 | 2019-07-31 | In process | Improvement Consultant, Project Assistants, Communications | Successful co-branding relationship built with MedChi in Maryland for recruitment, evaluating other opportunities with other stakeholders.
| Develop feedback mechanism for LAN participants to promote suggested topics of interest for future events. | 2015-01-01 | 2019-07-31 | Ongoing | Improvement Consultant, | Poll conducted at end of every webinar. Monitoring open rates and click rates for In Practice and online modules. Evaluating other options for feedback.
| Maintain a list of potential training topics for LAN participants. | 2014-11-12 | 2019-07-31 | Started/Ongoing | Improvement Consultant | List of training topics developed and added to as educational opportunities are identified.
| Develop and maintain a quarterly physician dashboard displaying progress of statewide LAN participants for certain Meaningful Use measures to identify high performers. | 2016-04-01 | 2019-07-31 | Not Started | Improvement Consultant
| Coordinate LAN activities with tasks B.1, B.2 and C.3 LANs. Possible collaborative LAN topics include: cultural competence, motivational interviewing, health literacy, reducing disparities, role of EHRs in disease management and prevention and care transitions. | 2015-01-01 | 2019-07-31 | In process | Task Improvement Consultants, LAN Manager | Regional cross task LAN planning meetings occur monthly to address integration of tasks and cross-cutting activities.
B.4.7 Monitoring and Reporting Requirements
| Create first draft of task work plan for B4. | 2014-08-22 | 2014-10-15 | Completed | Improvement Consultant
| Review work plan weekly to ensure activities are on track and develop action plan if needed. | 2014-09-01 | 2019-07-31 | Ongoing | Improvement Consultant | Weekly Team meetings are held to discuss work plans
| Complete timely monthly documentation of task activities to COR. | 2014-08-01 | 2019-07-31 | Ongoing | Improvement Consultant
| Track and review internal quality measures to assess progress and develop action plan when needed. | 2014-08-01 | 2019-07-31 | Ongoing | Improvement Consultant, State Program Director, Quality Improvement Director | CIQIP
| Complete and submit quarterly Task Report by state with overall summary. | 2014-11-05 | 2019-07-31 | Ongoing | Improvement Consultant, State Program Director, Project Assistant
B.4.8 Sustainability Plan
| Evaluate feedback received from LAN participants to assess their motivation for participating in QIN-QIO program and address their needs for continued engagement; incorporate recommendations into Sustainability Plan. | 2014-10-03 | 2019-07-31 | Ongoing | Improvement Consultant,
| Develop and maintain beneficiary recruitment list to ensure necessary participation is met for every LAN activity. | 2015-04-01 | 2019-07-31 | Ongoing | Improvement Consultant, | Beneficiaries recruited in both MD and VA, but seeking to expand the number of available participants through direct outreach at fairs and advertising through AARP and other stakeholders.
| Throughout the contract timeframe, rotate facilitation responsibility of the QRIP Advisory Committee on yearly basis to allow for ownership and sustainment of the Committee. | 2015-04-01 | 2019-07-31 | Ongoing | Improvement Consultant, State Program Director | Plans include rotating facilitation responsibility as network continues to develop.
Risk Mitigation Strategies to ensure Success
| Target challenged EPs for technical assistance by including both non-participating and participating physicians in LAN events; create dedicated email address for LAN participants to submit questions for technical assistance for MU, PQRS, and VM. | 2014-10-02 | 2019-07-31 | Ongoing | Improvement Consultant | All providers are encourage to participate. Q&A is available after all events, contact information is provided on all resources and tools.
| Continue communication with VHIT (VA REC) to ensure overlap of technical assistance is minimized. | 2014-10-02 | 2019-07-31 | Ongoing | Improvement Consultant
| Over recruit participants to maintain recruitment levels throughout the contract. | 2014-08-01 | 2019-07-31 | Ongoing | Improvement Consultant | Recruitment continues.
| Researching and sharing best practices to meet Meaningful Use and implement other strategies for improving prevention measures with Health Information Technology. | 2014-08-01 | 2019-07-31 | Ongoing | Improvement Consultant | Collaboration with D1 task and other Physicians Services projects
| Maintain engagement with participants through email updates (online community), active participation in LAN events, peer to peer mentoring. | 2014-08-01 | 2019-07-31 | Ongoing | Improvement Consultant, , Communications
Plan to Avoid Duplication of Effort
| Develop Patient Engagement strategy across all tasks so we have one "pool" of beneficiaries to recruit from. | 2015-01-01 | 2019-07-31 | Ongoing | Improvement Consultant, , Communications | Collaborated with Communications to develop a "Patient & Family Network" Volunteer Interest Form. Launched form in 2nd Quarter 2015. Master list of volunteers maintained by Communications staff.
| Develop database listing stakeholders/partners to ensure coordination and integration between tasks. | 2014-09-15 | 2019-07-31 | Ongoing | Improvement Consultant, IT staff
| Develop Regional Advisory Committee to include partners, stakeholders, beneficiaries, and VHQC staff for the Quality Reporting and Incentive Programs Network. | 2014-10-02 | 2019-07-31 | In process | Improvement Consultant, , Communications

## Task C.1 (hidden)
De-obligated as of 9/30/16 Per Modification 4
| Activity (detailed description of activities necessary to complete each task) | Start | Finish | Status | Personnel Resources | Notes
C.1.2 Provider Hospital Recruitment
| Identify 10SOW providers and recruit for CAUTI, CLABSI, CDI, VAE work in ICU and Med/Surg units. | 2014-08-01 | 2014-09-01 | Completed | Improvement Consultant
| Perform a scan using Hospital Compare data to identify and recruit providers who have an increased SIR in either CLABSI, CAUTI, or CDI. | 2014-08-01 | 2015-07-31 | Completed | Improvement Consultant
| Develop and maintain recruitment database with contact information and history of encounters. | 2014-08-01 | 2015-07-31 | Completed | Improvement Consultant
| Collaborate with HEN stakeholders to perform a scan to identify and recruit additional providers with open deficiencies and increased SIR's. | 2014-10-01 | 2015-07-31 | Completed | Improvement Consultant
| Phone calls to identified provider IP's beginning with 10SOW participants and then moving forward with new providers. | 2014-09-01 | 2015-07-31 | Completed | Improvement Consultant
| Send letter to provider CEO to make initial contact, with copies to IP and QI. | 2014-08-01 | 2014-10-01 | Completed | Communications
| Conduct kickoff webinar to review project goals. | 2014-10-01 | 2014-10-01 | Completed | Improvement Consultant, LAN Manager, Communications
| Complete follow-up calls and/or emails to participants attending kickoff webinar. | 2014-10-06 | 2014-12-31 | Completed | Improvement Consultant
| Collaborate with local/regional/national stakeholders to promote HQI's activities and aid in recruitment of members such as HENs, VHHA, Virginia Department of Health, Maryland Health Care Commission, Maryland Hospital Association, Maryland and Virginia APIC, Maryland Patient Safety Center and Maryland Department of Health and Mental Hygiene. | 2014-08-01 | 2015-07-31 | Completed | Improvement Consultant, Communications
| Contact hospitals systems, concentrating on Systems in which targeted hospitals are included. Utilize an integrated presentation for a HQI Team approach to recruit targeted hospitals. Team includes HQI IP, HQI analyst and Improvement consultant for quality reporting of HAI's | 2014-10-01 | 2015-07-31 | Completed | Improvement Consultant, State Program Director, IDIQ Director
| Engage hospital leadership for recruitment after the IP and/or Quality Director has been notified of the HAI Improvement Network and recruitment has not occurred | 2015-01-01 | 2015-07-31 | Completed | Improvement Consultant, State Program Director, | Most current HAI data for the hospitals were shared with the Leadership when contacted
| Collaborate with recruited providers to suggest and support other providers for the HAI Improvement Network participation | 2015-01-01 | 2015-07-31 | Completed | Improvement Consultant | Request made to network providers to invite other providers to the network during the monthly sharing calls.
C.1.3 Beneficiary and Family Engagement
| Engage providers, stakeholders and HQI staff to identify individuals to participate in a patient family advisory role. | 2014-08-01 | 2016-09-30 | Completed | Improvement Consultant
| Identify hospitals that include patients on their councils in order to include them in regional patient and family engagement committees, councils and education. | 2015-01-01 | 2016-09-30 | Completed | Improvement Consultant | 1.)Request providers to share patient and family engagement strategies during the HAI Network monthly sharing call. 2.)Identify hospitals that promote Patient and Family Engagement on their websites to assist in gaining HAI team involvement. 3.)Patient and Family Engagement practices discussed during one-on-one calls. 4.) First Beneficiary assessment tool sent to providers Oct. 2015
| Engage and utilize the NCC for patient and family contacts and stories for use during LAN activities | 2015-02-01 | 2016-09-30 | Completed | Improvement Consultant | Utilize Patient Family Centered Care Partners
| Develop participatory roles for patients and family advisors in developing and presenting quarterly LAN activity. | 2015-03-01 | 2016-09-30 | Completed | Improvement Consultant | A subgroup of consumers has been established to support efforts with specific education on topics they will work on with the advisory group members.
| Include some aspect of patient and family engagement in each LAN and prevention activity. | 2014-11-01 | 2016-09-30 | Completed | Improvement Consultant | Patient stories and resources for PFE are shared on monthly calls, providers are encouraged to identify Patient and family engagement activities in their hospital
| Provide onboarding packet that includes information about QIN, Acronyms, Helpful Resources (Hospital Compare). | 2014-08-01 | 2015-10-31 | Completed | Improvement Consultant, Communications | Consumer Education for HAI Advisory Group started 6/24/15
| Utilize the HQI's online community and or website to highlight Patient and Family stories. | 2015-05-31 | 2016-09-30 | Completed | Improvement Consultant, Communications
| Share patient stories with key stakeholders such as HENs, VHHA, Virginia Department of Health, Maryland Health Care Commission, Maryland Hospital Association, Maryland and Virginia APIC, Maryland Patient Safety Center and Maryland Department of Health and Mental Hygiene to share with their membership lists. | 2014-11-01 | 2016-09-30 | Completed | Improvement Consultant, Communications
| Monitor, assess, and report out the degree in which hospital providers engage beneficiaries/ patients and /or their family members and /or patient representatives. | 2015-08-01 | 2016-09-30 | Completed | Improvement Consultant, Communications | 1.)Assessment is made during 1:1 calls and sharing calls. 2.)Measurement will continue with updates for member tracking of performance improvement 3.)First Beneficiary assessment tool sent to providers Oct. 2015
C.1.4 Partner and Stakeholder Recruitment and Collaboration
| Contact stakeholders to secure written commitment for the work with HQI on the 11 SOW . The written commitment outlines the purpose of partnership and statement that the partnership will not duplicate efforts. | 2014-09-01 | 2016-09-30 | Completed | Improvement Consultant | Commitments obtained include but are not limited to Virginia Department of Health, HRET/VHHA Hospital Engagement Network, Mid-Atlantic Renal Coalition, VHHA, Virginia Department of Health, Maryland Health Care Commission, Maryland Hospital Association, Premier Hospital Engagement Network, Maryland and Virginia APIC, Maryland Patient Safety Center and Maryland Department of Health and Mental Hygiene.
| Conduct planning calls when needed with key stakeholders (HENs, VHHA, Virginia Department of Health, Maryland Health Care Commission, Maryland Hospital Association, Maryland and Virginia APIC, Maryland Patient Safety Center and Maryland Department of Health and Mental Hygiene) to discuss and plan upcoming HAI Prevention activities. | 2014-12-01 | 2016-09-30 | Completed | Improvement Consultant
| Enlist key stakeholder assistance in provider recruitment efforts (HENs, VHHA, Virginia Department of Health, Maryland Health Care Commission, Maryland Hospital Association, Maryland and Virginia APIC, Maryland Patient Safety Center and Maryland Department of Health and Mental Hygiene). | 2014-10-01 | 2015-07-31 | Completed | Improvement Consultant | MD Hospital Association has agreed to distribute letter of endorsement to hospital CEO's who have not already signed to participate. CMS to contact providers who have not signed up for the Network if they have excess HAIs
| Enlist stakeholder involvement to participate in quarterly statewide HAI advisory council. | 2015-01-01 | 2016-09-30 | Completed | State Program Director, Improvement Consultant | 1.) Virginia HAI Advisory Group was convened in March including stakeholders from VDH, VHHA, APIC, and others. Subgroups were formed and reported activities at the June Advisory group meeting. 2.) HQI is an active participant on the MD HAI Advisory Committee that is directed by the Maryland Health Care Commission. Improvement Consultant attends the monthly meetings via teleconference or in person.
| HQI will transition work to all HIINs awarded contracts in Maryland and Virginia | 2016-09-01 | 2016-09-30 | Completed | Improvement Consultant, State Program Director, HQI Analyst, Communications | HQI will: 1) Provide an orientation to HQI’s strategic approach for carrying out the HAI work, including lessons learned; 2) Review the status of activities that were in progress at the time of contract transition; 3) Offer to provide technical assistance for accessing NHSN data, such as obtaining an NHSN account and requesting hospitals to confer NHSN rights; and 4) Offer to participate in transition events the HIIN deems useful for its hospitals, such as a webinar that relates the QIN-QIO HAI initiative to the HIIN HAI initiative.
C.1.5.1 General HAI Tasks
| Post on the online community and/or distribute by email Infection Prevention resources including (but not limited to) CUSP, CAUTI, VAE, CLABSI, CDI, Hand Hygiene, ASP. | 2015-05-31 | 2016-09-30 | Completed | Improvement Consultant, Communications | 1.) One-on- one onboarding calls used to reinforce the use of the online community. 2.) January 2016 Education Tab added to Infection Prevention Community
| Develop and distribute a "start up" package outlining the HAI participation requirements including data submission timelines, data goals and deliverables, calendar of events (webinars, lunch and learn calls, coaching calls, regional meetings, quarterly data review, etc.). | 2015-01-01 | 2015-10-31 | Completed | Improvement Consultant, Communications | 1.) Checklist and team roster distributed during the first LAN call in January. A Zip file with all needed onboarding materials emailed in April, 2015. Continued onboarding with any new recruited hospital. 2.) Continued onboarding with any new recruited hospital include 1:1 calls to discuss custom preferences and roll out the project work to the hospital teams that are in place. We provide technical assistance as needed to confer rights to NHSN data for both HQI and the NCC.
| Perform a facility needs assessment and gap analysis of the infection prevention and quality improvement programs to identify areas of improvement in order to customize assistance for each provider | 2015-05-31 | 2015-10-31 | Completed | Improvement Consultant, Communications | 1.) A checklist and baseline assessment tool was developed and has been used with calls to individual providers that documents contact info, type and elements of their IP program. 2.) Onboarding and 1:1 calls completed utilizing the checklist to assess and identify gaps in PI activities that include but are not limited to Infection Prevention reporting, teamwork, leadership, and clinical best practice baselines.
| Develop a specific HAI assessment tool to be used to identify gaps around hospital process of EBP and best practice that are proven strategies to reduce HAI. | 2015-08-01 | 2016-06-30 | Completed | Improvement Consultant | This assessment tool is being developed using the results of the baseline assessment where gaps and barriers were identified. Beneficiary Engagement Assessment began Oct. 2015
| Review training history with facilities and document previous CUSP and TeamStepps training. | 2015-07-31 | 2015-10-31 | Completed | Improvement Consultant | This has been included in the checklist mentioned in line 32
| Develop and present a boot camp, workshop or webinar presenting the TeamSTEPPS process. | 2015-07-31 | 2015-12-31 | Completed | Improvement Consultant, Communications, | HQI supported the AHRQ TeamSTEPPS webinar series and sent them out as a calendar appointments. All providers were advised to sign up for the webinars and watch them live or recorded.
| Develop and present a boot camp or webinar presenting the CUSP process, using staff from hospitals to be instructors if any providers do not have previous training. | 2015-07-31 | 2015-12-31 | Completed | Improvement Consultant, Communications, | Most providers state that they have had some formal CUSP training and/or have participated in a CUSP initiative. The CUSP training videos used by the CUSP4MVP are shared with providers who do not have training or would like to refresh their knowledge.
| Distribute a Learning from Defects Tool for each HAI, CAUTI, CLABSI, CDI. | 2015-02-01 | 2016-09-30 | Completed | Improvement Consultant, Communications
| Develop recognition program to recognize and celebrate high-performing hospitals. | 2014-10-01 | 2015-07-31 | Completed | Improvement Consultant, Communications | HQI Award definitions and criteria have been established
| Identify and share best practices between providers through online community and/or LAN events. | 2014-12-01 | 2016-09-30 | Completed | Improvement Consultant
| Develop internal quality improvement team as needed based on monthly data analysis and performance. | 2016-01-01 | 2016-09-30 | Completed | IDIQ Director, State Program Director, Lean Six Sigma Manger, Improvement Consultant | Aggregated CLASBI data is demonstrating that Maryland will not reach contract evaluation measure for performance June 2015 - May 2016. Internal quality improvement team implemented. Will continue through September 30, 2016 [until CLASBI rates have met evaluation measure(s)].
| Distribute 2015 HQI Quality Innovation Awards to high-performing hospitals | 2016-03-01 | 2016-08-30 | Completed | Improvement Consultant, HQI Analyst, Communications
| Distribute HQI MVHIN participation certificates to participating hospitals, including recognition of high or top-performing facilities | 2016-08-01 | 2016-09-30 | Completed | Improvement Consultant, HQI Analyst, Communications
C.1.5.2 Collaboration with QIN NCC
| Develop a template/spreadsheet or use a template from the NCC to include all elements of the quarterly environmental scan. | 2014-10-01 | 2015-01-15 | Completed | Improvement Consultant, Analytics, NCC | HQI was Instructed that the NCC will provide this map to send out to QIN/QIO's
| Develop a map or use a map template from the NCC to visualize the elements of the environmental scan for quarterly review. | 2014-10-01 | 2016-09-30 | Completed | Improvement Consultant, Analytics, NCC | HQI Analyst updates disparities maps whenever new hospital compare data is available. Maps include gender, age and race.
| Provide national and regional benchmarking data from NCC to providers. | 2014-12-01 | 2016-09-30 | Completed | Improvement Consultant, Analytics, NCC | Monthly individual hospital and quarterly network reports include state and national benchmarking data.
| Disseminate evidence-based tools from NCC to providers. | 2014-12-01 | 2016-09-30 | Completed | Improvement Consultant, Communications, NCC | NCC provider Webinar series are sent to providers as a calendar invite
| Develop a road map or cross walk of resources for each Infection Prevention area to share with providers. | 2014-09-01 | 2016-09-30 | Completed | Improvement Consultant, Communications | The online community was used to distribute resources.
C.1.6.1 CLABSI
| Review the most recent hospital compare data quarterly to identify all providers in the state with a CLABSI SIR of >1.0. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | Hospital performance is assessed and feedback given on a monthly and quarterly basis.
| Request providers to submit any possible CLABSI's to HQI's IP for review using either an internal RCA type form or the HQI provided LfD analysis tool. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | Will utilize NHSN reports to trigger early ID of events and follow up with RCA and support resources from HQI.
| Present regional and or state CLABSI data quarterly during LAN webinars. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | Quarterly Network data reviewed on scheduled calls.
| Distribute CLABSI performance data monthly to the providers. | 2015-05-01 | 2016-09-30 | Completed | Improvement Consultant | 1st Monthly report sent to participating hospitals with cohort comparisons. 1st report distribution April 17,2015
| Conduct follow-up one on one call to providers after the monthly CLABSI data is distributed. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | First data report with 2015 data was distributed in June 2015. Providers with excess Infections are being contacted.
| Review CLIP protocol with providers and document that they are following the CLIP bundle for central line insertions. | 2015-07-31 | 2016-09-30 | Completed | Improvement Consultant | The CDC CLABSI checklist is used to identify gaps in clinical best practice that have been proven to reduce these infection events.
| Utilize the CDC TAP assessment starting with hospitals with excess CLABSIs to identify gaps in the hospital CLABSI prevention program | 2016-05-01 | 2016-09-30 | Completed | Improvement Consultant | 1.) The CDC released a draft CLABSI TAP Facility Assessment that was reviewed with low performing hospitals. It was a recommended component of the CLABSI performance improvement plan, and 5/6 low-performing hospitals in Maryland submitted CLABSI TAP Facility Assessments for analysis by CDC staff. 2.) The NHSN TAP ranking and CAD are included on Monthly data reports and discussed during one to one calls and TA.
| Conduct site visits with HQI and hospital Leadership when facilities continue to have CLABSI SIR >1.0. | 2015-07-31 | 2016-09-30 | Completed | Improvement Consultant, State Program Director, IIDIQ Director | Analysis and evaluation of possible site visits early 2016 HQI identified hospitals performing poorly in CLABSI in both states and conducted onsite CLABSI event and NHSN reporting validation. These site visits were conducted in partnership with MHCC in Maryland
C.1.6.2 CAUTI
| Review the most recent hospital compare data quarterly to identify all providers in the state with a CAUTI SIR of >1.0. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | Hospital performance is assessed and feedback given on a monthly and quarterly basis.
| Request providers to submit any possible CAUTI's to HQI IP for review using either an internal RCA type form or the HQI provided LfD analysis tool. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | Will use NHSN reports to trigger early ID of events and follow up with RCA and support resources from HQI.
| Present regional and or state CAUTI and SDUR data during LAN events. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant, Communications | Quarterly Network data reviewed on scheduled calls.
| Distribute CAUTI and SDUR performance data monthly to the providers. | 2015-05-01 | 2016-09-30 | Completed | Improvement Consultant | 1st Monthly report sent to participating hospitals with cohort comparisons. 1st report distribution April 17,2015
| Conduct follow-up one on one call to providers after the monthly CAUTI and SDUR data is distributed. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | First data report with 2015 data was distributed in June 2015. Providers with excess Infections are being contacted.
| Conduct site visits with HQI and hospital Leadership when facilities continue to have CAUTI SIR >1.0. | 2015-07-31 | 2016-09-30 | Completed | Improvement Consultant, State Program Director, IDIQ Director | Analysis and evaluation of possible site visits early 2016
| Distribute tools to assist providers to accurately monitor and decrease urinary catheter device days (prevalence studies, validation rounds, etc.) | 2015-07-31 | 2016-09-30 | Completed | Improvement Consultant, Communications | CAUTI TAP Tools and CDC website shared with providers followed by phone calls to answer questions and assist with distribution of the CAUTI TAP baseline assessment.
| Conduct phone calls and/or site visits to monitor, evaluate, validate and perform device prevalence study with any provider who fails to decrease SDUR. | 2015-01-01 | 2016-09-30 | Completed | Improvement Consultant
| Utilize the CDC TAP assessment starting with hospitals with excess CAUTI's to identify gaps in the hospital CAUTI prevention program | 2015-09-01 | 2016-09-30 | Completed | Improvement Consultant, Analytics | 1.) The CDC CAUTI TAP Facility Assessment tool has been introduced to the Network members, and three hospitals completed these assessments for CDC analysis. 2.) The TAP ranking and CAD are included on Monthly data reports and discussed during one to one calls and TA.
| Collaborate with VHHA who is leading the 9th cohort of the "CUSP: Stop CAUTI" Initiative in order to offer educational webinars to HQI providers | 2015-01-01 | 2015-08-31 | Completed | Improvement Consultant | Cohort CUSP work ended and all resources are housed on AHRQ website provided to our members on our online community and on LAN calls.
C.1.6.3 CDI
| Review the most recent hospital compare data quarterly to identify all providers in the state with a CDI SIR of >1.0. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | Hospital performance is assessed and feedback given on a monthly and quarterly basis.
| Request providers to submit any possible CDI's to HQI's IP for review using either an internal RCA type form or the HQI provided LfD analysis tool. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | Will utilize NHSN reports to trigger early ID of events and follow up with RCA and support resources from HQI.
| Present regional and or state CDI data during LAN activities. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant, Communications | Quarterly Network data review are scheduled calls.
| Distribute CDI performance data monthly to the providers. | 2015-05-01 | 2016-09-30 | Completed | Improvement Consultant | 1st Monthly report sent to participating hospitals with cohort comparisons. 1st report distribution April 17,2015
| Conduct follow-up one on one call to providers after the monthly CDI data is distributed. | 2015-05-31 | 2016-09-30 | Completed | Improvement Consultant | First data report with 2015 data was distributed in June 2015. Providers with excess Infections are being contacted.
| Conduct site visits with HQI and hospital Leadership when providers continue to have CDI SIR >1.0. | 2015-07-31 | 2016-09-30 | Completed | Improvement Consultant, State Program Director, IDIQ Director | Analysis and evaluation of possible site visits early 2016.
| Conduct a scan after recruitment commitment to evaluate ASP progress of providers. | 2015-07-31 | 2016-09-30 | Completed | Improvement Consultant | 1.) An ASP Affinity group has been formed to include key stakeholders from both states. 2.) A standardized tool was developed and distributed. 3.) The findings will be shared with hospital leads. 4.) Follow-up to be conducted as necessary to further engage those leaders to substantially support their individual hospital's ASP. 5.) ASP assessment tool distributed and completed with results and executive summary feedback to participating hospitals 11-17-15 6.) ASP Affinity Group has agreed to align efforts with the newly formed MD Campaign for Appropriate Antibiotic USE (CAAUSE).
| Provide ASP education, and support by identifying mentor providers with effective ASP to share their practice and policy. | 2015-07-31 | 2016-09-30 | Completed | Improvement Consultant | 1.) Collaborative work with regional stakeholders including state pharmacy organizations, state health departments, state hospitals associations and other state stakeholders to align and assess state and regional educational and resource needs to enhance ASPs. 2.) CAAUSE met with MD Hospital Association for recruitment and to provide education and learnings from the Affinity Group ASP Assessment tool.
| Provide support for the C.2 Nursing Home CDI task | 2016-05-01 | 2016-09-30 | Completed | Improvement Consultant | 1.) HQI Infection Preventionist attended NCC training modules in order to understand the requirement for NHs to register, join and report in NHSN. 2.) HQI Infection Preventionist will support nursing homes in the application process for gaining access to NHSN. 3.) HQI Infection Preventionist will provide needed technical assistance for NHs to complete the annual survey, set up monthly reporting plans, report data in to NHSN and run analysis reports from that data.
C.1.6.4 VAE
| Train and assist providers with the elements of VAE reduction using current evidenced based best practices to include, not limited to, VAE reporting and surveillance definitions and interventional strategies | 2015-07-31 | 2016-09-30 | Completed | Improvement Consultant, Communications | 1.) The June 2015 VAE webinar series offered by the NCC for the network providers was shared with current members. New members will have the recording and supporting documents available. 2.) Feb 2015 JH Armstrong Institute CUSP4MVP HQI Cohort started.
| Train and assist providers with reporting VAE using NHSN | 2015-06-01 | 2016-09-30 | Completed | Improvement Consultant, Communications | The June 2015 VAE webinar series offered by the NCC for the network providers was shared.
| Monitor NHSN VAE reports to identify providers who are not reporting and providers who have VAE events | 2016-08-01 | 2019-07-31 | Not started | Improvement Consultant
| Request providers to submit any possible VAE's to HQI's IP for review using either an internal RCA type form or the HQI provided LfD analysis tool. | 2016-08-01 | 2019-07-31 | Not started | Improvement Consultant
| Present regional and or state VAE data during LAN activities. | 2016-08-01 | 2019-07-31 | Not started | Improvement Consultant, Communications
| Conduct follow-up one on one call to providers after the monthly VAE data is distributed. | 2016-08-01 | 2019-07-31 | Not started | Improvement Consultant
| Establish and include baseline VAE data in reports to the NCC and providers | 2017-07-31 | 2018-07-31 | Not started | Improvement Consultant
C.1.7 Learning and Action Networks
| Identify provider mentors that have utilized best practices and decreased their HAI SIR's to share on webinars. | 2014-10-01 | 2016-09-30 | Completed | Improvement Consultant, Communications | 1.) Identified mentors/best practices during the recruitment phase. 2.) Utilize HAI Network data reports to identify potential mentors. 3.) Utilize the CAUTI TAP reports that provide unit rankings in the states to identify mentor hospitals.
| Identify patient and family stories to share on webinars and in publications. | 2014-10-01 | 2016-09-30 | Completed | Improvement Consultant, Communications
| Develop and present a webinar event educating providers on VAE prevention, surveillance and reporting in NHSN. | 2015-06-01 | 2015-07-31 | Completed | Improvement Consultant, Communications | The June 2015 VAE webinar series offered by the NCC for the network providers was shared
| Conduct at least quarterly LAN regional Team Meetings to review and compare HAI data, share best practices, review NHSN reporting, gather educational and tool development needs. | 2015-01-01 | 2016-09-30 | Completed | Improvement Consultant, Communications | The first data sharing call was in May 2015 where YTD 2014 data was presented and reviewed. Quarterly calls were continued throughout the work.
| Conduct monthly small group calls by dividing each state into three regions to promote sharing of best practices, create synergy and reduce duplicative work. | 2016-01-01 | 2016-09-30 | Completed | Improvement Consultant, Communications | 1.) Consideration of provider participation in a HEN was used to create small groups in each state by assigning a group to each HEN operating in the state and any provider not in a HEN in the third group. 2.) These calls will be used to identify infection prevention gaps, barriers, successes and needs.
| Conduct focus group calls for specific Infection Prevention topics as needed | 2016-01-01 | 2016-09-30 | Completed | Improvement Consultant, Communications | 1.) Any ongoing infection prevention issues or barriers identified during the small group calls and/or the quarterly data review calls will be addressed by scheduling a focus call. 2.) The topics and invited providers will be needs based though out the contract. 3.) Convened CLASBI focus group call with low performing CLASBI providers.
| Conduct annual webinar, conference or meeting (preferably face to face) to review the state HAI data and educational needs. | 2015-11-01 | 2019-07-31 | Not Started | Improvement Consultant, Communications
| Use one of the annual events to provide education on an ASP. | 2015-05-01 | 2016-09-30 | Completed | Improvement Consultant, Communications
| Partner with Virginia APIC to sponsor and/or present webinars and provide education on HAI prevention topics. | 2015-10-01 | 2016-09-30 | Completed | Improvement Consultant, Communications | 1.) HQI provided education pertaining to certification in Infection Prevention at the 2015 Virginia APIC conference in October 2015. 2.) HQI to partner with APIC VA and VDH to present a webinar series on 2016 NHSN surveillance and reporting changes.
| Conduct webinars/teleconferences/sharing call on HAI prevention topics determined from providers suggestions. | 2014-12-01 | 2016-09-30 | Completed | Improvement Consultant, Communications | October sharing call included presentation and analysis of the CLABSI data requested by APIC provider member.
| Integrate activities with other tasks to achieve operational efficiencies and coordinated communications to providers. | 2014-08-01 | 2016-09-30 | Completed | Improvement Consultant, Communications, State Program Director | 1) September 2015, HQI assisted with planning and conducting a regional infection prevention educational event for nursing homes through the New River Valley Cross setting Council. 2.) A second education event for the Roanoke Valley, VA Nursing homes was held in April 2016.
| Partner with key stakeholders to share HQI sponsored webinars through their membership and/or distribution lists (VDH, VHHA, Maryland and Virginia APIC, Maryland Health Care Commission, Maryland Hospital Association and Maryland Patient Safety Center). | 2014-12-01 | 2016-09-30 | Completed | Improvement Consultant, Communications, Key Stakeholders | Partnering with VHHA to share the 9th cohort of CAUTI CUSP with HQI providers. Share Webinar announcement with Stakeholders for distribution.
C.1.8 Monitoring and Reporting Requirements
| Use Hospital Compare and other identified data sources to perform the monthly environmental scans of the HQI providers at the state level. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant, Analyst | New Internal Tracking report developed based on NHSN data to determine individual hospital performance impact on the network.
| Populate a map with the monthly environmental scan results. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant, Analyst | HQI maps developed comparing HAI rates to disparities such as age and race
| Develop a tracking system to log all tool development and distribution, best practices, patient and stakeholder activities. | 2014-10-31 | 2015-12-01 | Completed | Improvement Consultant, IT
| Complete timely monthly documentation of task activities to COR. | 2014-08-01 | 2016-09-30 | Completed | Improvement Consultant
| Track and review internal quality measures to assess progress and develop action plan when needed. | 2014-08-01 | 2016-09-30 | Completed | Improvement Consultant, State Program Director, Lean Six Sigma Manager
| Submit quarterly Task Report by state and overall summary. | 2014-11-05 | 2016-09-30 | Completed | Improvement Consultant, State Program Director
| Streamline reporting method to make it easier for providers and leadership to review and utilize data. | 2016-01-31 | 2016-09-30 | Completed | Improvement Consultant, IT | Utilize "box" application
| Explore and utilize defect analysis tools submitted by providers for all HAI's to be used and shared with HQI in order to determine valid HAI data submission. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | 1.) State validation reports for Maryland providers released 4th QTR 2015. These will be used for MD prover validation. 2.) Virginia Department of Health is currently validating Virginia providers. 3.) HQI is partnering with VDH when issues are identified with HQI provider submission. VDH completed state validation early 2016.
C.1.9 Sustainability Plan
| Promote and disseminate proven best practices and models of improvement like CUSP, TeamSTEPPS, from national organizations like AHRQ, IHI, CDC. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | 1.) Partnering with VHHA to share the 9th cohort of CAUTI CUSP with HQI providers in MD and VA. 2.) Share Webinar announcement with Stakeholders for distribution. 3.) Education tab added to Online Community for 24-7 access by providers
| Provide program evaluation and encourage providers to use proven QI like PDSA to hardwire changes. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant
| Work with stakeholders to develop and disseminate a Train-the-Trainer Toolkit that includes best practices, resources, and stakeholder information. | 2014-11-01 | 2016-09-30 | Completed | Improvement Consultant | This toolkit has been started with the onboarding packet which will be converted after recruitment as a base for the HAI toolkit.
| Throughout the contract timeframe rotate facilitation responsibility of the Virginia HAI Advisory Council in order to allow for ownership and sustainment of the Council. | 2014-11-01 | 2016-09-30 | Completed | Improvement Consultant, Stakeholders | Subgroups formed with leads who are accountable for each group.
| Begin sustainability plan at beginning of contract. Explore why and what would motivate hospitals to continue to champion the work and progress made by the HAI Improvement Network after the contract ends. | 2014-11-01 | 2016-09-30 | Completed | Improvement Consultant | Plans in place for the Virginia HAI Advisory Group to be a sustainable group of stakeholders with or without HQI involvement. HQI in partnership with VDH has developed a crosswalk for stakeholder engagement and reporting requirements directed at the Virginia state providers.
Risk Mitigation Strategies to ensure Success
| Coordinate and plan projects with HENs to eliminate duplication of effort. | 2014-10-01 | 2016-09-30 | Completed | Improvement Consultant | HEN contract awarded in October 2015 for one year; HQI is reaching out to current HENS recruiting in VA and MD to identify shared providers and partnership opportunities.
| Establish clear reporting guidelines including deadlines for monthly reporting when HAI work begins. | 2014-10-01 | 2015-07-31 | Completed | Improvement Consultant | 30 days out report reviewed on monthly calls starting 10-2015
| Communicate regularly with recruited providers for feedback and topics for education and tool development. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | Reminders on monthly calls and follow-up call email.
| Over recruit hospitals to maintain an active and diverse LAN. | 2014-10-01 | 2015-07-31 | Completed | Improvement Consultant | Hospital recruitment exceeds targets in both states.
| Maintain engagement with participants through monthly communication to promote active participation in LAN events, peer to peer mentoring. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | Webinar topics and education requests shared on monthly sharing calls
| Utilize established, successful resources, best practices already proven and produced like CUSP and TeamSTEPPS. | 2014-10-31 | 2016-09-30 | Completed | Improvement Consultant | CAUTI CUSP 9th cohort content calls used for CAUTI education and resources.
| Review lessons learned from 10SOW to identify and avoid barriers to success and involvement in LAN. | 2014-09-01 | 2015-07-31 | Completed | Improvement Consultant
| Utilize LAN data/feedback to conduct an assessment of the HAI Improvement Network. | 2014-10-01 | 2016-09-30 | Completed | Improvement Consultant | Evaluation feedback reviewed after each call. Debrief with presenters following the calls to identify opportunities and lessons learned.
Plan to Avoid Duplication of Effort
| Conduct planning calls when needed with key stakeholders (HENs, Maryland and Virginia APIC, MD/VA pharmacy organizations, MDHMH, VDH, VHHA, Maryland Hospital Association, Maryland Health Care Commission, and Maryland Patient Safety Center) to plan and discuss state wide LAN activities that can be shared among all providers. | 2014-11-01 | 2016-09-30 | Completed | Improvement Consultant, Communications | To avoid duplicative efforts, the ASP Affinity group and Virginia HAI ASP subgroup have joined efforts to developed and distribute the ASP baseline assessment tool. Intensive efforts began 8-2015
| Collaborate with HEN's to determine what prevention work will be performed by each organization and who will contact each shared provider. | 2014-10-01 | 2016-09-30 | Completed | Improvement Consultant | Upon HEN award contract in Oct. Contact has been made with the Premier HEN to obtain a list of early HEN members on both MD and VA. Alignment planning has begun to eliminate overlap and provide efficiency for the MVHIN members and the QIN and HENs. HQI and VHHA have set monthly meeting dates to identify partnership opportunities for HAI prevention
| Stakeholder LAN events will be shared and utilized if relevant to the HAI work for HQI monthly LAN events or webinars. | 2014-10-01 | 2016-09-30 | Completed | Improvement Consultant | HQI is collaborating with VHHA to use the CAUTI CUSP program as CAUTI education; HQI shares all open educational events with VHHA, VDH and APIC. HQI shares all open educational events with VHHA, VDH and APIC Recruiting for the Johns Hopkins MVP Cohort 3. HQI is a Coordinating entity.
| Before developing any new tool, education, webinar, etc. check with stakeholders to see if something has already been developed. | 2014-10-01 | 2016-09-30 | Completed | Improvement Consultant | MDHMH- HQI - Matrix tool to identify ongoing clinical improvement projects within the state developed by HQI and shared with MDHMH and other interested stakeholders.

## Instructions
Culturally and Linguistically Appropriate Services (CLAS) Action Plan
The Culturally and Linguistically Appropriate Services (CLAS) help organizations address the cultural and communication barriers many individuals face when seeking services. The action plan was developed to enable organizations to easily assign and track the progress of the standards implemented based on the implementation checklist for the National CLAS standards. The CLAS Action Plan (CLAS AP) tab lists all activities on the implementation checklist, including space to add specific organizational activities. For each activity, assign a team member responsible for the activity and set a due date for when the activity should be completed. Commit to how often you will review the action plan (e.g., weekly, bi-weekly, monthly), check the action plan, and determine your progress status by selecting from the drop-down menu your status as Started, In Progress, or Completed. Make any notes of barriers or challenges that would impede the success of implementation and document your mitigation strategies to overcome barriers. Your QIA would provide resources and link them to the action plan as needed. You can also make any other helpful notes at the bottom of the document that you want the team to know as you update the action plan. This material was prepared by Health Quality Innovators (HQI), a Quality Innovation Network-Quality Improvement Organization (QIN-QIO) under contract with the Centers for Medicare & Medicaid Services (CMS), an agency of the U.S. Department of Health and Human Services (HHS). Views expressed in this material do not necessarily reflect the official views or policy of CMS or HHS, and any reference to a specific product or entity herein does not constitute endorsement of that product or entity by CMS or HHS. 12SOW/HQI/QIN-QIO-0528-04/25/23

## CLAS Standards
What is CLAS?
CLAS stands for culturally and linguistically appropriate services. CLAS is services that are respectful of and responsive to each person’s culture and communication needs. CLAS helps your organization take into account cultural health beliefs, preferred languages, health literacy levels, and communication needs.
The National CLAS standards are intended to advance health equity, improve quality, and help eliminate health care disparities by establishing a blueprint for health and health care organizations to:
Principal Standard
1. Provide effective, equitable, understandable, and respectful quality care and services that are responsive to diverse cultural health beliefs and practices, preferred languages, health literacy, and other communication needs.
Governance, Leadership and Workforce
2. Advance and sustain organizational governance and leadership that promotes CLAS and health equity through policy, practices, and allocated resources.
3. Recruit, promote, and support a culturally and linguistically diverse governance, leadership, and workforce that are responsive to the population in the service area.
4. Educate and train governance, leadership, and workforce in culturally and linguistically appropriate policies and practices on an ongoing basis.
Communication and Language Assistance
5. Offer language assistance to individuals who have limited English proficiency and/or other communication needs, at no cost to them, to facilitate timely access to all health care and services.
6. Inform all individuals of the availability of language assistance services clearly and in their preferred language, verbally and in writing.
7. Ensure the competence of individuals providing language assistance, recognizing that the use of untrained individuals and/or minors as interpreters should be avoided.
8. Provide easy-to-understand print and multimedia materials and signage in the languages commonly used by the populations in the service area.
Engagement, Continuous Improvement, and Accountability
9. Establish culturally and linguistically appropriate goals, policies, and management accountability, and infuse them throughout the organization's planning and operations.
10. Conduct ongoing assessments of the organization's CLAS-related activities and integrate CLAS-related measures into measurement and continuous quality improvement activities.
11. Collect and maintain accurate and reliable demographic data to monitor and evaluate the impact of CLAS on health equity and outcomes and to inform service delivery.
12. Conduct regular assessments of community health assets and needs and use the results to plan and implement services that respond to the cultural and linguistic diversity of populations in the service area.
13. Partner with the community to design, implement, and evaluate policies, practices, and services to ensure cultural and linguistic appropriateness.
14. Create conflict and grievance resolution processes that are culturally and linguistically appropriate to identify, prevent, and resolve conflicts or complaints.
15. Communicate the organization's progress in implementing and sustaining CLAS to all stakeholders, constituents, and the general public.
Source: https://thinkculturalhealth.hhs.gov/clas/standards

## CLAS AP
[INSERT Organization Name] CLAS Action Plan Based on the Implementation Checklist for the National CLAS Standards
Activity | Assigned To: | Due By: | Status | Barriers/Challenges | Mitigation strategies | Resources
Complete the Implementation Checklist for the National CLAS Standards
Review the background information in the "CLAS Standards" tab of this spreadsheet. | [5 empty] | An Implementation Checklist for the National CLAS Standards (hhs.gov)
Designate a CLAS Champion or Champions to complete the checklist
Complete the Implementation Checklist (Pages 4-7) at Think Cultural Health
Review the results of the CLAS Checklist & complete the CLAS Action Worksheet with a focus on practices checked as "planning to implement"
Work with the organization's internal team and a HQI team member to estabish an organization's full CLAS Action Plan using this template
Add practices that you plan to implement in the NEXT MONTH
Add organizational-specific activity
Add organizational-specific activity
Add organizational-specific activity
Add practices that you plan to implement in the NEXT 3 MONTHS
Add organizational-specific activity
Add organizational-specific activity
Add organizational-specific activity
Add practices that you plan to implement in the NEXT 6 MONTHS
Add organizational-specific activity
Add organizational-specific activity
Add organizational-specific activity
Theme 1: Governance, Leadership, and Workforce
Provide support to the designated CLAS Champion, whose specific responsibilities include (at a minimum) continuous learning about, promoting, and identifying and sharing educational resources about CLAS throughout the organization
Use your completed CLAS Action Plan to develop and implementation plan with start/finish timeline and notes to make assignments and add details. Get endorsement and support from the organization's leadership
Add organizational-specific activity
Add organizational-specific activity
Add organizational-specific activity
Add organizational-specific activity
Theme 2: Communication and Language Assistance
Complete an organizational assessment specific to language assistance services to describe existing language assistance services and to determine how they can be more effective and efficient
Standardize procedures for staff members and train staff in those procedures. For example, ask all new patients what language they prefer to speak and read, and if they would like an interpreter. Record patients' language assistance needs in the medical record
Provide individuals with notification that describes what communication and language assistance is available, in what languages the assistance is available, and to whom they are available. For patients who do not speak enough English to respond to questions about language preference, use "I Speak" cards | [5 empty] | For patients who do not speak enough English to respond to questions about language preference, use "I Speak" cards (PDF, 317.25 KB) to identify the language they speak.
Require that all individuals serving as interpreters complete certification or other formal assessments of linguistic and health care terminology skills to demonstrate competency
Consider financial and/or human resource (e.g. time off) incentives to staff who complete interpreter training and meet assessment criteria
Formalize processes for translating materials into languages other than English and for evaluating th quality of these translaions
Theme 3: Engagement, Continuous Improvement, and Accountability
Incorporate CLAS into mission, vision, and/or strategic plans
Tailor existing evaluation efforts to include measures of CLAS implementation
Complete a CLAS-related organizational assessment
Provide training to staff on REAL data | [5 empty] | Simple Strategies for Data Collection Training (hqin.org)
Collect race, ethnicity, and language (REAL) data | [5 empty] | Simple Strategies for Collecting REAL Data (hqin.org)
Use REAL data
Collaborate with stakeholders and community members in community health needs assessment data collection, analysis, and reporting efforts
Include community members in the process of planning programs and develo
Consdier using staff as cultural brokers to help improve feedback machanisms, conflict resolution process, and communication with culturally and liguistically diverse individuals
Partner with community organizations to lead discussions about the services provided and progress made and to create advisory boards on pertinent issues
Notes

## LIst (hidden)
Started
In Progress
Completed

## SIP 1 MD-Stopping Sepsis in LTC (hidden)
| Activity (detailed description of activities necessary to complete each task) | Start | Finish | Status | Personnel Resources | Notes
SIP 1 Provider Recruitment
| Create and maintain a database of the skilled nursing facilities that transfer the greatest number of residents with sepsis to the 21 hospitals participating in Maryland Hospital Association - Maryland Patient Safety Center's Improving Sepsis Survival Collaborative. These nursing homes will be prioritized for recruitment. | 2015-10-01 | 2015-10-31 | Completed | Improvement Consultant
| Develop and send recruitment letter with specific messaging to targeted nursing facilities Executive Leadership from Executive Leadership of the hospitals participating in the Maryland Hospital Association and Maryland Patient Safety Improving Sepsis Survival Collaborative. | 2015-10-15 | 2015-11-30 | Completed | Communications, Improvement Consultant
| Identify targeted nursing homes for the Sepsis Initiative that are currently participating in the C.2 Nursing Home Improvement Network to maximize recruitment efforts. | 2015-10-01 | 2015-12-31 | Completed | Improvement Consultant
| Request stakeholder groups to support and promote recruitment activities i.e. send messages of support to providers, promote Reducing Sepsis in LTC recruitment events in newsletters, etc. | 2015-10-01 | 2015-12-31 | Completed | Improvement Consultant, Communications | Stakeholder groups to include but not limited to Maryland Hospital Association, Maryland Patient Safety Center, Health Facilities Association of Maryland, Lifespan, etc.
| QIO representative to schedule 1:1 meetings with corporate leaders and/or nursing facility providers as needed. | 2014-10-01 | 2015-12-31 | Completed | Improvement Consultant, State Program Director, IDIQ Director
| Distribute QIN-QIO and Nursing Home Improvement Network and Reducing Sepsis in Long Term Care fact sheets to providers, corporate leaders, and stakeholders. | 2015-11-01 | 2015-12-31 | Completed | Improvement Consultant, Communications
Engagement
| Conduct kick-off session for recruited nursing homes. | 2015-10-01 | 2016-01-31 | Completed | Improvement Consultant, Communications
| Baseline performance data provided to Phase 1 nursing homes. | 2016-01-01 | 2016-02-28 | Completed | Improvement Consultant, Analytic Support
| Initial correlation analysis of relationship between hospital sepsis mortality rates and admissions for sepsis from nursing homes. | 2016-01-01 | 2016-02-28 | Completed | Improvement Consultant, Analytic Support
| Identify, develop, and provide LTC sepsis screening and awareness tools. | 2015-12-15 | 2015-02-28 | Completed | Improvement Consultant
| Implementation of LTC sepsis screening and awareness tools by nursing homes. | 2016-01-30 | 2016-03-31 | Completed | Improvement Consultant | All facilities have been provided implementation tools and education. Continuing to monitor and provide support
| Develop and provide presentation toolkit for resident/family council meeting. | 2016-01-01 | 2016-03-31 | Completed | Improvement Consultant
| Sepsis affinity group established to include sharing calls for nursing homes. | 2016-02-01 | 2018-01-15 | In progress | Improvement Consultant | Invite Infection preventionist and other HQI experts, Maryland Hospital Association (MHA) representatives and Maryland Patient Safety Center (MPSC) representatives.
| Identify nursing homes with highest sepsis hospital admission rates and request to complete on line infection prevention assessment | 2016-03-31 | 2016-09-30 | Completed | Improvement Consultant | Utilized the CDC Infection Prevention assessment to develop an online tool for the facilities to complete
| Results of assessments to be reviewed to identify areas for improvement | 2016-07-01 | 2016-10-31 | Completed | Improvement Consultant
| Technical assistance provided to help nursing homes with highest sepsis rates modify policies/procedures, make small test of change, and measure results. | 2016-04-01 | 2018-01-15 | Ongoing | Improvement Consultant
| Technical assistance will be provided to the 10 nursing homes with the most hospital admissions for sepsis on at least one of the following: admission assessment, change in condition, or laboratory testing. | 2016-09-01 | 2018-01-15 | Ongoing | Improvement Consultant
| Develop LTC sepsis risk assessment tool and train nursing homes on tool. | 2017-06-01 | 2017-07-31 | Completed | Improvement Consultant
| Assist nursing homes with implementation of the sepsis risk assessment/evaluation tool | 2017-08-01 | 2018-01-15 | Ongoing | Improvement Consultant
| Conduct site visits to provide technical assistance for the nursing homes with the highest sepsis hospital admission rates using 2016 claims data | 2017-09-01 | 2017-12-31 | In progress | Improvement Consultant
| Host regional sepsis forums for nursing homes and hospitals | 2017-09-01 | 2017-11-30 | In progress | Improvement Consultant
Partner and Stakeholder Collaboration
| Meet with the Maryland Hospital Association (MHA) and the Maryland Patient Safety Center (MPSC) to discuss the data and to align our work efforts to integrate the identified nursing homes into a cohesive sepsis reduction effort. | 2015-10-01 | 2018-01-15 | Ongoing | HQI Maryland State Director, Improvement Consultant | Having regular scheduled conference calls - review timeline and progress on each call
| Invite stakeholders such as the MHA, MPSC, LifeSpan, Health Facilities Association of Maryland, and APIC to participate in project activities i.e. participant or guest speaker for education sessions, review and/or development of resource materials, provide resource materials, etc. | 2015-10-01 | 2018-01-15 | Ongoing | Improvement Consultant | HQI spoke at leading edge Maryland Sharing call
| Utilize, adapt, and share resources developed by and/or used in the MHA-MPSC: Improving Sepsis Survival Collaborative with recruited nursing homes. | 2015-03-01 | 2018-01-15 | Ongoing | Improvement Consultant | MPSC shared hand hygiene work on March 2016 webinar
Rapid Cycle QI Testing and Implementation
| Improvement Consultants to assist facilities with setting and monitoring improvement goals for rapid cycle improvement. | 2015-03-01 | 2018-01-15 | Ongoing | Improvement Consultant | PDSA reviewed during kick off webinar on 1/14/16 and example of PDSA demonstrated
| Utilize evidence based practices and best practices to provide proven strategies that facilities can be used as test(s). | 2015-03-01 | 2018-01-15 | Ongoing | Improvement Consultant
| Assist facilities with developing systems to collect real time data for improvement analysis. | 2015-03-01 | 2018-01-15 | Ongoing | Improvement Consultant, Analytic Support | Demo data collection tools during February and March 2016 webinar & provided teaching tools in April 2016
Monitoring and Data Collection
| Utilization and analysis QI data to measure for nursing home progress. | 2016-01-01 | 2018-01-15 | Ongoing | Improvement Consultant, Analytic Support
| 1:1 data review/analysis with providers to conduct RCA. | 2016-09-01 | 2018-01-15 | Ongoing | Improvement Consultant | conducting 1:1 sessions with top 10
| 1:1 data review/analysis with providers to identify best practices. | 2016-09-01 | 2018-01-15 | Ongoing | Improvement Consultant
| Track and review internal quality measures to assess progress and develop action plan when needed. | 2015-11-01 | 2018-01-15 | Ongoing | Improvement Consultant, State Program Director, Quality Improvement Director
Sustainability Plan
| Integrate sustainability in training sessions. | 2016-01-01 | 2018-01-15 | Ongoing | Improvement Consultant
| Utilize system assessment tools in order to assess gaps and facilitate sustainability readiness. | 2016-01-01 | 2018-01-15 | Ongoing | Improvement Consultant
| Include working across task and healthcare settings to accomplish integrated goals of sustainability. | 2016-01-01 | 2018-01-15 | Ongoing | Improvement Consultant
Risk Mitigation Strategies to ensure Success
| Coordinate and plan projects with Maryland Patient Safety Center and Maryland Hospital Association to promote integration and cooperation between nursing homes and hospitals. | 2015-10-01 | 2018-01-15 | Ongoing | Improvement Consultant
| Seek feedback and input from providers and stakeholders regarding barriers. | 2015-10-31 | 2018-01-15 | Ongoing | Improvement Consultant
Plan to Avoid Duplication of Effort
| Coordinate activities with stakeholder activities by sharing events and monitoring calendars (MHA, MPSC, Virginia Health Care Association, HFAM, LifeSpan, and LeadingAge Maryland). | 2015-10-01 | 2018-01-15 | Ongoing | Improvement Consultant | Actively participating in stakeholder meetings to stay abreast of current activity and to share mutual activities.
| Schedule activities in combination with stakeholder events as possible. | 2015-10-31 | 2018-01-15 | Ongoing | Improvement Consultant
| House links to other stakeholder resources in on-line community. | 2016-01-01 | 2018-01-15 | In progress | Improvement Consultant

## SIP 2 - Advanced Care Managemt (hidden)
SIP-2 Advanced Care Planning in the ACO Setting Project Work Plan, revised 10/15/2017
Task | Activity (detailed description of activities necessary to complete each task) | Start | Finish | Status | Personnel Resources | Notes
Provider Recruitment
Project Year 1 | Recruit Cohort 1 Signature Partner/Inova employed physician practices that utilize Inova Fairfax Hospital and Inova Mount Vernon Hospital. Recruit Inova Fairfax and Inova Mount Vernon Hospitals | 2015-08-18 | 2016-01-01 | Completed | Project Manager/Signature Partners
| Meet with Signature Partners/Inova, C-TAC (until 5/2016), Capital Caring and HQI team members to initiate and continue project communication | 2015-09-29 | 2018-01-15 | ongoing | All core project work group staff
| Develop and send recruitment messaging to Inova Stakeholders. Send out press release | 2015-08-18 | 2015-11-30 | Completed | Communications, Project Manager
| Conduct Advanced Illness Program Kick-Off Session for Inova Medical Group practices and Key Operational Partners | 2015-08-18 | 2016-03-03 | Completed | All core project work group staff | This was done as a face to face meeting in Falls Church, VA
Project Year 2 | Recruit Cohort 2 Signature Partner/Inova independent physician practices that utilize Inova Fairfax Hospital and Inova Mount Vernon Hospital. Recruit Inova Fairfax and Inova Mount Vernon Hospitals | 2015-08-18 | 2016-03-03 | Completed | Project Manager/Signature Partners
Engagement
Project Year 1 & 2 | C-TAC and HQI will conduct Cohort 1 Inova/Signature Partner Practice Site Assessments to include operational capabilities and gap analysis: *Identify local project stakeholders *Organize workgroups with participants and subject matter experts *Assess advanced illness population opportunities and business models *Assess strategic alignment opportunities *Assess practice culture/perceptions/barriers about advanced illness care | 2015-10-20 | 2015-12-31 | Completed | Project Management Group, to include IDIQ Director | On-site assessment completed the first week of December, 2015
| Baseline performance data completed for Cohort 1 and Cohort 2 Inova Medical Group practices through Medicare Claims review | 3/3/2016 | 4/28/2016 | Completed | Project Manager, HQI analyst, IDIQ Director
Project Year 1 & 2 | Provide patient level data to ACO for review of eligible patients to begin/continue enrollment | 3/3/2016 | 2017-11-30 | Transition to Sustainability | Project Manager, HQI analyst, Signature Partners, IDIQ Director
| Perform sample chart review to confirm initial potential patient population | 2016-04-28 | 2016-05-09 | Completed | Signature Partners | The results demonstrated this program would be beneficial for this sample
Project Year 1 & 2 | Care Model Operational Design: Hospital and Practice Capability Assessments conducted to review: *Workflow redesigns *Staffing *Internal and External Care Coordination/Partnerships *EHR Documentation *Team structure *Care/Conversation Guidelines *Identification of advanced illness patient *Transitions of Care *Current completion of Advanced Directives/POST | 1/1/2016 Review for Cohort 2 7/31/16 | 5/31/2016 Complete 8/31/2016 | Completed | Project Manager, Inova, Signature Partners, IDIQ Director | Inova hired an Advanced Illness Project Manager to provide onsite oversight of care model implementation and sustainability.
| Develop program tools to operationalize care model Finalize above * items | 5/25/16 Review for Cohort 2 7/31/16 | 6/30/2016 Complete 7/31/16 | Completed | Project Manager, Inova, Signature Partners, IDIQ Director
Project Year 1 & 2 | Training and project implementation: *Start with small groups of office physicians and office staff to provide time to minimize barriers *Practice "The Conversation" using Roleplay without patients *Provide clinician feedback and coaching *Spread to Physician Practice level | 6/1/2016 Initiate for Cohort 2 10/1/2016 | 7/31/2016 Complete 12/31/2016 | Continue to collect data on project patients until 11/30/2017 | Project Manager, Inova, Signature Partners | Coaching continues with the Inova project team transition
Begin to enroll patients in the Advanced Illness Program from primary care physician office referrals
*Start with small groups of hospitalists and case management staff to provide time to minimize barriers *Practice "The Conversation" using Roleplay without patients *Provide clinician feedback and coaching *Spread to Inpatient level at Inova Fairfax and Mount Vernon Hospitals
Begin to enroll patients in the Advanced Illness Program from acute care inpatient referrals
Project Year 1 & 2 | Provide an overview of Ariadne Labs Serious Illness Care Community of Practice for Inova's consideration for a private space to collaborate between interdisciplinary teams implementing an Advanced Illness Program. https://portal.ariadnelabs.org/groups/community-of-practice | 2016-05-31 | 2018-01-15 | ongoing | Project Manager | Provides updated resources, videos, and webinars, as well as, the virtual community. Currently with members across the country
Partner and Stakeholder Collaboration
Project Year 1 & 2 | Orient community organizations and stakeholders to the project with an educational outreach model. Then the community can provide support for local older adults and their families about the importance of having conversations about advanced directives, goals and wishes, and end - of - life planning | 2015-11-15 | 2018-01-15 | ongoing | Project Manager, Communications
| Support Inova in promoting Advance Care Planning during Palliative Care and Hospice Month. Inova will sponsor Community Palliative Care Day | 2016-11-01 | 2016-11-30 | Completed | Project Manager, Communications
| Integrate HQI Patient and Family Advisory Council into SIP-2 project | 2016-06-01 | 2017-08-31 | Completed | Project Manager, HQI Program Integration Manager
Monitoring and Data Collection
Project Year 1 & 2 | Cohort 1 begins/continues collecting data on enrolled patient population | 2016-07-31 | 2017-11-30 | ongoing | Project Manager, HQI Analyst, Signature Partners Quality Manager
Project Year 1 & 2 | Cohort 2 begins/continues collecting data on enrolled patient population | 2016-12-31 | 2017-11-30 | ongoing | Project Manager, HQI Analyst, Signature Partners Quality Manager
| Submit CMS developed template for Quarterly Reports | 2016-02-05 | 2017-11-05 | Completed with QR through October, 2017 | Project Manager, IDIQ Director
| Submit CMS draft final report | 2017-04-15 | 2017-11-15 | In progress | Project Manager, IDIQ Director, Communications
| Submit CMS final contract report | 2017-06-15 | 2017-12-15 | In progress | Project Manager, IDIQ Director, Communications
Risk Mitigation Strategies to ensure Success
Project Year 1 & 2 | Seek feedback and input from providers and stakeholders regarding barriers | 2015-10-31 | 2017-10-31 | Transition to Sustainability | Project Manager
Project Year 1 & 2 | Integrate across tasks to facilitate broad risk mitigation | 2015-07-01 | 2017-09-30 | Completed | Project Manager
Plan to Avoid Duplication of Effort
Project Year 1 & 2 | Coordinate activities with stakeholder activities by sharing events and monitoring calendars | 2015-10-31 | 2018-01-15 | Ongoing | Project Manager | Actively participating in stakeholder meetings to stay abreast of current activity and to share mutual activities
| Schedule activities in combination with stakeholder events as possible | 2015-10-31 | 2018-01-15 | Ongoing | Project Manager
| Share SIP successes and lessons learned with other QIN-QIOs | as opportunities present | 2018-01-15 | as opportunities present | Project Manager
| Submit CMS final contract report | 2017-06-15 | 2017-12-15 | In progress | Project Manager, State Program Director, Communication Team
Sustainability Plan
| Integrate Advanced Care Model as Inova spreads to the Advanced Care Illness Clinic, Housecall Program and Skilled Nursing Facility Hospitalist program | 2016-07-31 | 2018-01-15 | In progress | Project Manager
| Inova and Capital Caring membership to Ariadne Labs Serious Illness Care Community of Practice for a private space to collaborate with other interdisciplinary teams implementing an Advanced Illness Program. https://portal.ariadnelabs.org/groups/community-of-practice | 2016-05-31 | 2018-01-15 | ongoing | Project Manager | Provides updated resources, videos, and webinars, as well as, the virtual community. Currently with members across the country